## Task Tracker
IT Department — Cross-Team Task Tracker 2026
Request ID | Task ID | Task Name | Team | Category | Dept Tag | Priority | Status | Stage | Phase | Assignee | Team Lead | Created Date | Deadline | Completed Date | Dependencies | Notes
| 10347513 | [Flex.MSP] Hệ thống điện chuyển mạch VSDC | MW Team | CR |  | Medium | Doing |  | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-07-03 10:21
2129248 | 10274446 | [CR] [2129248] [RMD] Add Special room information for Locations | Dev Team B | CR | RMD | Medium | UAT | UAT Testing | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-06-19 09:39 | 2026-06-29 23:59 | 2026-07-02 16:03
2335404 | 10223433 | [CR] [2335404] [RMD] Upgrade the automatic limit adjustment feature on Customer Portal Admin | Dev Team B | CR | RMD | Medium | UAT | UAT Testing | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-06-08 13:50 | 2026-06-12 23:59 | 2026-06-12 08:16 | 2335404
2084592 | 10055830 | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | Dev Team B | CR | RMD | High | UAT | UAT Testing | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-05-05 17:37 | 2026-05-15 23:59 | 2026-05-16 08:01 | 2084592
2084592 | 9739419 | [CR] [2084592] [RMD] Declare Limit & Type For Account Using Special Product on FLEX system | Team Mobile | CR | RMD | High | Overdue | UAT Testing | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-05-31 23:59 |  | 2084592
2149046 | 9739414 | [CR] [2149046] [IT] EKYC | Team Mobile | CR | IT | High | Overdue | UAT Testing | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-05-22 23:59 |  | 2149046
2283752 | 9739427 | [CR] [2283752] [SS] Send Notification via Elite App and mail all right issue | Team Mobile | CR | SS | Low | UAT | UAT Testing | Q2 |  | phongvo@phs.vn | 2026-03-03 16:40 |  |  | 2283752
2238356 | 9739415 | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | Team Mobile | CR | MSD | High | Overdue | UAT Testing | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-05-29 23:59 |  | 2238356
2335404 | 9953694 | [CR] [2335404] Upgrade the automatic limit adjustment feature | Team Mobile | CR |  | Medium | Doing | FTL Coding | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:22 |  |  | 2335404
2330515 | 10340145 | [CR] [2330515] [RMD] IPO Share Subscription Feature | Dev Team B | CR | RMD | Low | Todo | Backlog | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:56 |  |  | 2330515
2415056 | 10340143 | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | Dev Team B | CR | MKT | Low | Doing | Discuss Req | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:55 |  |  | 2415056
2425861 | 10340127 | [CR] [2425861] [RS] Research Portal: Phase 2 | Dev Team B | CR | RS | Low | Todo | Backlog | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:55
2426812 | 10340024 | [CR] [2426812] [MKT] Merge CCC & RS chatbot into one Master Client Chatbot | Dev Team B | CR | MKT | Low | Doing | Design UI/UX | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:44
2403987 | 10340021 | [CR] [2403987] [SS] Loyalty System - Phase 1 | Dev Team B | CR | SS | Low | Doing | Web B Coding | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:42
2540233 | 10340020 | [CR] [2540233] [SS] FIFA WORLD CUP CHALLENGE 2026 | Dev Team B | CR | SS | Low | Todo | Dev To do | Q3 | VÕ BẢO MINH | minhvo@phs.vn | 2026-07-02 08:42 |  |  | 2540233
1954732 | 10058431 | [CR] [1954732] [HR] HR report automation | Dev Team B | CR | HR | Low | Todo | Dev To do | Backlog | VÕ BẢO MINH | minhvo@phs.vn | 2026-05-06 08:34
1923581 | 9956873 | [CR] [1923581] [RMD] Tool to control the number of positions that need to be closed out | Dev Team B | CR | RMD | Low | Blocked | Pending | Backlog | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:25
2403987 | 10059258 | [CR] [2403987] [SS] Loyalty System - Phase 1 - Login Screen | Dev Team B | CR | SS | Low | UAT | UAT Testing | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-05-06 13:54
2275303 | 9956507 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Dev Team B | CR | SS | Medium | Done | Ready for go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:17 | 2026-05-04 23:59 | 2026-05-05 17:43 | 2275303
2400155 | 9956961 | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | Dev Team B | CR | MKT | Medium | Done | Go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:43 | 2026-06-26 23:59 | 2026-06-29 08:17 | 2400155
2423945 | 10055837 | [CR] [2423945] [SS] Enhance the promotional declaration feature on the Admin Portal | Dev Team B | CR | SS | Low | Done | Go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-05-05 17:48 |  | 2026-06-01 08:11
2154685 | 9956498 | [CR] [2154685] [BMD] Upgrade fund certificate trading feature on Mobile app | Dev Team B | CR | BMD | Medium | Done | Go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:15 | 2026-04-28 23:59 | 2026-05-05 14:36 | 2154685
2385402 | 9956496 | [CR] [2385402] [MKT] Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | Dev Team B | CR | MKT | Low | Done | Go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:15 |  | 2026-04-25 09:17
2197982 | 9956499 | [CR] [2197982] [RS] Research Landing Page: All Features & Phase 1 Execution | Dev Team B | CR | RS | Low | Done | Go-live | Q2 | VÕ BẢO MINH | minhvo@phs.vn | 2026-04-14 09:16 |  | 2026-04-20 08:28
2506884 | 10334131 | [CR] [2506884] [LG] Touchpoint for products | Team Mobile | CR | LG | Low | Todo | Backlog | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:35
2526008 | 10334133 | [CR] [2526008] [LG] Goal-based tool phase 2 and Touchpoint for tool | Team Mobile | CR | LG | Low | Todo | Backlog | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:35
2482578 | 10209339 | [CR] [2482578] [AC] Upgrade the QR Code Deposit Function on the PHS App | Team Mobile | CR | AC | Low | Todo | Backlog | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-06-05 09:49
2216483 | 10334127 | [CR] [2216483] [MSD] Loyalty system on mobile app (phase 2) | Team Mobile | CR | MSD | Low | Doing | Web B Coding | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:34 |  |  | 2216483
2540233 | 10334124 | [CR] [2540233] [MSD] FIFA WORLD CUP CHALLENGE 2026 | Team Mobile | CR | MSD | Low | Doing | Discuss Req | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:33 |  |  | 2540233
2415056 | 10209283 | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | Team Mobile | CR | MKT | Low | Todo | Backlog | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-06-05 09:47 |  |  | 2415056
2310394 | 10334126 | [CR] [2310394] [AC] Tax analysis and estimation tools for investors (phase 2) | Team Mobile | CR | AC | Low | Blocked | Waiting FTL | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:33 |  |  | 2310394
2291957 | 10209368 | [CR] [2291957] [IC] Update the account opening function on the PHS Elite app login screen | Team Mobile | CR | IC | Low | Doing | Discuss Req | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-06-05 09:54
2397922 | 9953690 | [CR] [2397922] [LG] Enhance filter for Elite Fund | Team Mobile | CR | LG | Low | Todo | Dev To do | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:21
2317336 | 9739425 | [CR] [2317336] [AC] Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | Team Mobile | CR | AC | Low | Doing | Design review | Q3 |  | phongvo@phs.vn | 2026-03-03 16:40
2330515 | 9953664 | [CR] [2330515] [RMD] IPO Share Subscription Feature | Team Mobile | CR | RMD | Low | Doing | Design UI/UX | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:11 |  |  | 2330515
2438262 | 10334129 | [CR] [2438262] [LG]_Goal-based Tool | Team Mobile | CR | LG | Low | Todo | Backlog | Q3 | VÕ THANH PHONG | phongvo@phs.vn | 2026-07-01 09:34
2289280 | 9739426 | [CR] [2289280] [FN] Future-Dated Withdrawal Scheduling for Customers | Team Mobile | CR | FN | Low | Todo | Dev To do | Q3 |  | phongvo@phs.vn | 2026-03-03 16:40 |  |  | 2289280
2307583 | 9953685 | [CR] [2307583] [LG] PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | Team Mobile | CR | LG | Low | Todo | Discuss Req | Backlog | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:18
2376660 | 9953687 | [CR] [2376660] [CCC] Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | Team Mobile | CR | CCC | Low | Todo | Backlog | Backlog | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:20
2174942 | 9739412 | [CR] [2174942] [MSD] Automation Test Proposal | Team Mobile | CR | MSD | Low | Blocked | Pending | Backlog | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39
2340654 | 10217565 | [CR] [2340654] [FN] [No.02-2026] Updated payment order form of IVB | MW Team | CR | FN | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-06-06 15:54 |  | 2026-06-06 15:56
2310394 | 10090312 | [CR] [2310394 - 2391899] [KT] [No.01-2026] Tax analysis and estimation tools for investors. | MW Team | CR | KT | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 09:03 |  | 2026-07-02 16:50 | 2310394
2446191 | 10090329 | [CR] [2446191] [MSD] [No.08-2026] VCF0051 – Adjust Report Extraction Conditions | MW Team | CR | MSD | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 09:09 |  | 2026-06-16 10:25
2222464 | 10090302 | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | MW Team | CR | RMD | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 09:00 |  | 2026-05-13 10:27 | 2222464
2443571 | 10090343 | [CR] [2443571] [SS] [No.09-2026] Restrict using PHS email address for securities transactions | MW Team | CR | SS | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 09:14 |  | 2026-06-05 11:06
2133352 | 10090240 | [CR] [2133352] [RMD] [No.12-2025] Margin product calculation tool | MW Team | CR | RMD | Medium | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:43 |  | 2026-05-15 10:32 | 2133352
2246969 | 10090247 | [CR] [2246969] [DTD] [No.39-2025] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | MW Team | CR | DTD | Low | Done | Go-live | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:45 |  | 2026-05-15 10:32
2275303 | 10090293 | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository features via the PHS Elite Trading application | MW Team | CR | DTD | Medium | Doing | FTL Coding | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:57 |  | 2026-07-02 16:49 | 2275303
2216483 | 10090287 | [CR] [2216483] [MSD] [No.33-2025] Loyalty Customer System (Core Flex) | MW Team | CR | MSD | Low | Blocked | Waiting FTL | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:55 |  | 2026-07-03 08:46 | 2216483
2238356 | 10090263 | [CR] [2238356] [MSD] [No.27-2025]ADVANCE MARGIN FOR DERIVATIVES | MW Team | CR | MSD | High | UAT | UAT Testing | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:52 |  |  | 2238356
2084592 | 10090209 | [CR] [2084592] [RMD] [No.10-2025] Calculate interest for accounts using special interest rate products | MW Team | CR | RMD | High | Blocked | Waiting FTL | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:33 |  |  | 2084592
2149046 | 10090204 | [CR] [2149046] [SS] [No.28-2025] Adjustment of the account opening flow on the PHS ELITE TRADING application | MW Team | CR | SS | High | UAT | UAT Testing | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:31 |  |  | 2149046
2106995 | 10090258 | [CR] [2106995] [DTD] [No.25-2025] Add put-through order trading feature on PHS ELITE XPRO | MW Team | CR | DTD | Low | UAT | UAT Testing | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:50
2283752 | 10090289 | [CR] [2283752] [DTD] [No.03-2026] Send Notification via Elite App and mail all right issue | MW Team | CR | DTD | Low | UAT | UAT Testing | Q2 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:56 |  |  | 2283752
2437753 | 10090323 | [CR] [2437753] [SS] [No.07-2026] AF & LN Duplication & Bulk Import Function | MW Team | CR | SS | Low | Doing | FSS Eval CR | Q3 | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 09:08
2289280 | 10090283 | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling for Customers | MW Team | CR | FN | Low | Todo | Discuss Req | Backlog | NGUYỄN MINH HỮU | huunguyen@phs.vn | 2026-05-12 08:53 |  |  | 2289280
2275303 | 9739429 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Team Mobile | CR | SS | Medium | Done | Go-live | Q2 |  | phongvo@phs.vn | 2026-03-03 16:40 | 2026-05-26 23:59 | 2026-06-29 14:10 | 2275303
2310394 | 9953652 | [CR] [2310394] Tax analysis and estimation tools for investors (Phase 1) | Team Mobile | CR |  | Low | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:05 |  | 2026-06-29 14:09 | 2310394
2400155 | 9953677 | [CR] [2400155] Marketing - Develop Mission Tracking Page for Promotion Q1.2026 | Team Mobile | CR |  | Medium | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-13 17:14 |  | 2026-06-29 14:09 | 2400155
2329940 | 9739428 | [CR] [2329940] [RS] AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | Team Mobile | CR | RS | Medium | Done | Go-live | Q2 |  | phongvo@phs.vn | 2026-03-03 16:40 | 2026-05-22 23:59 | 2026-06-05 09:44
2306127 | 9931785 | [CR] [2306127] INB_ Proposal to implement the mobile app notifications for Elite Seeds | Team Mobile | CR |  | Low | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-09 17:00 |  | 2026-05-27 13:29
2372910 | 10007137 | [CR][2372910] [RESEARCH] Permission to get API data from OpenAcc web | Team Mobile | CR |  | Low | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-24 09:27 |  | 2026-05-04 08:26
2216483 | 9739424 | [CR] [2216483] [MSD] LOYALTY SYSTEM ON MOBILE APP | Team Mobile | CR | MSD | Low | Done | Go-live | Q2 |  | phongvo@phs.vn | 2026-03-03 16:39 |  | 2026-05-04 08:15 | 2216483
2400512 | 9931751 | [SDK] [2400512] Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google | Team Mobile | SDK |  | Low | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-04-09 16:57 |  | 2026-04-20 08:12
2222464 | 9739423 | [CR] [2222464] [RMD] Add sign-in method | Team Mobile | CR | RMD | Low | Done | Go-live | Q2 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 |  | 2026-04-20 08:11 | 2222464
2212813 | 9739422 | [CR] [2212813] [SS] Derivatives Order Placement UI Enhancement | Team Mobile | CR | SS | Low | Done | Go-live | Q2 |  | phongvo@phs.vn | 2026-03-03 16:39 |  | 2026-04-13 17:02
2133352 | 9739420 | [CR] [2133352] [RMD] Margin product calculation tool | Team Mobile | CR | RMD | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-03-30 23:59 | 2026-03-30 15:00 | 2133352
2247969 | 9739418 | [CR] [2247969] [SS] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | Team Mobile | CR | SS | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-03-30 23:59 | 2026-03-30 15:00
2186435 | 9739416 | [CR] [2186435] [MSD] PROMOTION REGISTRATION FUNCTION UPGRADE | Team Mobile | CR | MSD | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-03-30 23:59 | 2026-03-30 14:59 | 2186435
2285823 | 9739417 | [CR] [2285823] [IC] THE LOGIN SCREEN GREETING MESSAGE | Team Mobile | CR | IC | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-03-16 23:59 | 2026-03-16 11:11
2224919 | 9739421 | [CR] [2224919] [SS] Feature to save multiple login accounts on a single device in the PHS Elite Trading app | Team Mobile | CR | SS | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:39 | 2026-03-16 23:59 | 2026-03-16 11:10
2302697 | 9739413 | [CR] [2302697] [LG] Add content regarding personal data protection | Team Mobile | CR | LG | Low | Rejected | Rejected | Q1 |  | phongvo@phs.vn | 2026-03-03 16:39 |  | 2026-03-06 08:59
2185585 | 9739430 | [CR] [2185585] [IT] Add the Reward Redemption feature to the PHS Elite Trading application | Team Mobile | CR | IT | Low | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2154685 | 9739431 | [CR] [2154685] [INB] Mutual Fund Distribution (Phase 2) | Team Mobile | CR | INB | Medium | Done | Go-live | Q1 |  | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41 | 2154685
| 9739432 | [MKT] Update Logo PHS 20 years anniversary | Team Mobile | Internal |  | Medium | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2077975 | 9739433 | [CR] [2077975] [MKT] Collaboration with Woori Bank Proposal | Team Mobile | CR | MKT | Low | Done | Go-live | Q1 |  | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2196774 | 9739434 | [CR] [2196774] [INB] Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | Team Mobile | CR | INB | Low | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2242463 | 9739435 | [CR] [2242463] [MSD] PROMOTION: HORSE YEAR FORTUNE 2026 | Team Mobile | CR | MSD | Low | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2185583 | 9739436 | [CR] [2185583] [IT] Enhancement of the Smart OTP Function on the PHS Elite Trading Application | Team Mobile | CR | IT | Low | Done | Go-live | Q1 | VÕ THANH PHONG | phongvo@phs.vn | 2026-03-03 16:40 |  | 2026-03-03 16:41
2213580 | 9739106 | [CR] [2213580] [CCC] Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | Dev Team B | CR | CCC | Low | Done | Go-live | Q1 | VÕ BẢO MINH | minhvo@phs.vn | 2026-03-03 15:47 |  | 2026-03-17 10:52
2186435 | 9739108 | [CR] [2186435] [MSD] Enhance Promotion features on Admin Customer Portal | Dev Team B | CR | MSD | Medium | Done | Go-live | Q1 | VÕ BẢO MINH | minhvo@phs.vn | 2026-03-03 15:47 | 2026-03-09 23:59 | 2026-03-10 08:47 | 2186435
2065876 | 9739105 | [CR] [2065876] [MSD] Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | Dev Team B | CR | MSD | Low | Done | Go-live | Q1 | VÕ BẢO MINH | minhvo@phs.vn | 2026-03-03 15:46 |  | 2026-03-04 06:56
1722552 | 9744376 | [CR] [1722552] [BMD] Provide API data source for Transaction fluctuation function in Broker portal | Dev Team B | CR | BMD | Medium | Done | Go-live | Q1 | VÕ BẢO MINH | minhvo@phs.vn | 2026-03-04 16:25 | 2026-02-13 23:59 | 2026-03-04 16:29

## CR Overview
CR Overview
Request ID | CR Title | Dept | Priority | Teams | Team Mobile | Dev Team B | MW Team | Overall Status | Notes
2084592 | Calculate interest for accounts using special interest rate products | RMD | High | 3 teams | Overdue | UAT | Blocked | Overdue | Team Mobile: overdue (deadline 31/05/2026)
2275303 | Enhance securities depository features via the PHS Elite Trading application | SS | Medium | 3 teams | Done | Done | Doing | Partially Done | MW Team: no deadline set
2149046 | EKYC | IT | High | 2 teams | Overdue | — | UAT | Overdue | Team Mobile: overdue (deadline 22/05/2026)
2238356 | ADVANCE MARGIN FOR DERIVATIVES | MSD | High | 2 teams | Overdue | — | UAT | Overdue | Team Mobile: overdue (deadline 29/05/2026)
2133352 | Margin product calculation tool | RMD | Medium | 2 teams | Done | — | Done | Done
2154685 | Upgrade fund certificate trading feature on Mobile app | BMD | Medium | 2 teams | Done | Done | — | Done
2186435 | PROMOTION REGISTRATION FUNCTION UPGRADE | MSD | Medium | 2 teams | Done | Done | — | Done
2335404 | Upgrade the automatic limit adjustment feature on Customer Portal Admin | RMD | Medium | 2 teams | Doing | UAT | — | In Progress | Team Mobile: no deadline set
2400155 | Develop Mission Tracking Page for Promotion | MKT | Medium | 2 teams | Done | Done | — | Done
2216483 | Loyalty system on mobile app (phase 2) | MSD | Low | 2 teams | Doing | — | Blocked | Blocked | Team Mobile: no deadline set
2222464 | Add sign-in method | RMD | Low | 2 teams | Done | — | Done | Done
2283752 | Send Notification via Elite App and mail all right issue | SS | Low | 2 teams | UAT | — | UAT | UAT
2289280 | Future-Dated Withdrawal Scheduling for Customers | FN | Low | 2 teams | Todo | — | Todo | Not Started
2310394 | Tax analysis and estimation tools for investors (phase 2) | AC | Low | 2 teams | Blocked | — | Done | Blocked
2330515 | IPO Share Subscription Feature | RMD | Low | 2 teams | Doing | Todo | — | In Progress | Team Mobile: no deadline set
2415056 | Implementation of “Partner Offers” on PHS Mobile App | MKT | Low | 2 teams | Todo | Doing | — | In Progress | Dev Team B: no deadline set
2540233 | FIFA WORLD CUP CHALLENGE 2026 | SS | Low | 2 teams | Doing | Todo | — | In Progress | Team Mobile: no deadline set
1722552 | Provide API data source for Transaction fluctuation function in Broker portal | BMD | Medium | 1 team | — | Done | — | Done
2129248 | Add Special room information for Locations | RMD | Medium | 1 team | — | UAT | — | UAT
2224919 | Feature to save multiple login accounts on a single device in the PHS Elite Trading app | SS | Medium | 1 team | Done | — | — | Done
2247969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | SS | Medium | 1 team | Done | — | — | Done
2285823 | THE LOGIN SCREEN GREETING MESSAGE | IC | Medium | 1 team | Done | — | — | Done
2329940 | AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | RS | Medium | 1 team | Done | — | — | Done
1923581 | Tool to control the number of positions that need to be closed out | RMD | Low | 1 team | — | Blocked | — | Blocked
1954732 | HR report automation | HR | Low | 1 team | — | Todo | — | Not Started
2065876 | Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | MSD | Low | 1 team | — | Done | — | Done
2077975 | Collaboration with Woori Bank Proposal | MKT | Low | 1 team | Done | — | — | Done
2106995 | Add put-through order trading feature on PHS ELITE XPRO | DTD | Low | 1 team | — | — | UAT | UAT
2174942 | Automation Test Proposal | MSD | Low | 1 team | Blocked | — | — | Blocked
2185583 | Enhancement of the Smart OTP Function on the PHS Elite Trading Application | IT | Low | 1 team | Done | — | — | Done
2185585 | Add the Reward Redemption feature to the PHS Elite Trading application | IT | Low | 1 team | Done | — | — | Done
2196774 | Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | INB | Low | 1 team | Done | — | — | Done
2197982 | Research Landing Page: All Features & Phase 1 Execution | RS | Low | 1 team | — | Done | — | Done
2212813 | Derivatives Order Placement UI Enhancement | SS | Low | 1 team | Done | — | — | Done
2213580 | Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | CCC | Low | 1 team | — | Done | — | Done
2242463 | PROMOTION: HORSE YEAR FORTUNE 2026 | MSD | Low | 1 team | Done | — | — | Done
2246969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | DTD | Low | 1 team | — | — | Done | Done
2291957 | Update the account opening function on the PHS Elite app login screen | IC | Low | 1 team | Doing | — | — | In Progress | Team Mobile: no deadline set
2302697 | Add content regarding personal data protection | LG | Low | 1 team | Rejected | — | — | Rejected
2306127 | INB_ Proposal to implement the mobile app notifications for Elite Seeds |  | Low | 1 team | Done | — | — | Done
2307583 | PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | LG | Low | 1 team | Todo | — | — | Not Started
2317336 | Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | AC | Low | 1 team | Doing | — | — | In Progress | Team Mobile: no deadline set
2340654 | Updated payment order form of IVB | FN | Low | 1 team | — | — | Done | Done
2372910 | [RESEARCH] Permission to get API data from OpenAcc web |  | Low | 1 team | Done | — | — | Done
2376660 | Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | CCC | Low | 1 team | Todo | — | — | Not Started
2385402 | Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | MKT | Low | 1 team | — | Done | — | Done
2397922 | Enhance filter for Elite Fund | LG | Low | 1 team | Todo | — | — | Not Started
2400512 | Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google |  | Low | 1 team | Done | — | — | Done
2403987 | Loyalty System - Phase 1 | SS | Low | 1 team | — | Doing | — | In Progress | Dev Team B: no deadline set
2423945 | Enhance the promotional declaration feature on the Admin Portal | SS | Low | 1 team | — | Done | — | Done
2425861 | Research Portal: Phase 2 | RS | Low | 1 team | — | Todo | — | Not Started
2426812 | Merge CCC & RS chatbot into one Master Client Chatbot | MKT | Low | 1 team | — | Doing | — | In Progress | Dev Team B: no deadline set
2437753 | AF & LN Duplication & Bulk Import Function | SS | Low | 1 team | — | — | Doing | In Progress | MW Team: no deadline set
2438262 | _Goal-based Tool | LG | Low | 1 team | Todo | — | — | Not Started
2443571 | Restrict using PHS email address for securities transactions | SS | Low | 1 team | — | — | Done | Done
2446191 | VCF0051 – Adjust Report Extraction Conditions | MSD | Low | 1 team | — | — | Done | Done
2482578 | Upgrade the QR Code Deposit Function on the PHS App | AC | Low | 1 team | Todo | — | — | Not Started
2506884 | Touchpoint for products | LG | Low | 1 team | Todo | — | — | Not Started
2526008 | Goal-based tool phase 2 and Touchpoint for tool | LG | Low | 1 team | Todo | — | — | Not Started
Summary
Total unique CRs:
Multi-team CRs:
CRs with Overdue status:
CRs fully Done:
CRs Partially Done:
CRs In Progress:
CRs in UAT:
CRs Blocked:
CRs Rejected:

## fact_task_snapshot
report_date | task_id | request_id | team | assignee | stage | stage_order | status | priority | phase | q_kpi | is_subtask | is_done | wip_flag | is_multi_team | team_count | has_deadline | sla_met | completed_late | late_days | days_to_deadline | age_days | cycle_time_days | lead_time_days | stale_days | risk_level | waiting_external | has_weekly_review | recommit_count
2026-07-03 | 10347513 |  | MW Team | NGUYỄN MINH HỮU |  |  | Doing | Medium | Q2 |  | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 0 |  |  |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10274446 | 2129248 | Dev Team B | VÕ BẢO MINH | UAT Testing | 5 | UAT | Medium | Q2 | 2026Q2 | FALSE | FALSE | TRUE | FALSE | 1 | TRUE | FALSE | TRUE | 2 |  | 14 | 13 | 259 |  | High | FALSE | FALSE | 1
2026-07-03 | 10223433 | 2335404 | Dev Team B | VÕ BẢO MINH | UAT Testing | 5 | UAT | Medium | Q2 | 2026Q2 | FALSE | FALSE | TRUE | TRUE | 2 | TRUE | TRUE | FALSE | 0 |  | 25 | 3 | 67 |  | High | FALSE | FALSE | 1
2026-07-03 | 10055830 | 2084592 | Dev Team B | VÕ BẢO MINH | UAT Testing | 5 | UAT | High | Q2 | 2026Q2 | FALSE | FALSE | TRUE | TRUE | 3 | TRUE | FALSE | TRUE | 0 |  | 59 | 10 | 224 |  | High | FALSE | FALSE | 1
2026-07-03 | 9739419 | 2084592 | Team Mobile | VÕ THANH PHONG | UAT Testing | 5 | Overdue | High | Q2 | 2026Q1 | FALSE | FALSE | FALSE | TRUE | 3 | TRUE |  | FALSE | 33 | -33 | 122 |  |  | 2 | High | FALSE | TRUE | 1
2026-07-03 | 9739414 | 2149046 | Team Mobile | VÕ THANH PHONG | UAT Testing | 5 | Overdue | High | Q2 | 2026Q1 | FALSE | FALSE | FALSE | TRUE | 2 | TRUE |  | FALSE | 42 | -42 | 122 |  |  | 3 | High | FALSE | TRUE | 0
2026-07-03 | 9739427 | 2283752 | Team Mobile |  | UAT Testing | 5 | UAT | Low | Q2 | 2026Q2 | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 122 |  |  | 2 | Medium | FALSE | TRUE | 0
2026-07-03 | 9739415 | 2238356 | Team Mobile | VÕ THANH PHONG | UAT Testing | 5 | Overdue | High | Q2 | 2026Q1 | FALSE | FALSE | FALSE | TRUE | 2 | TRUE |  | FALSE | 35 | -35 | 122 |  |  | 2 | High | FALSE | TRUE | 0
2026-07-03 | 9953694 | 2335404 | Team Mobile | VÕ THANH PHONG | FTL Coding | 3 | Doing | Medium | Q2 | 2026Q3 | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 81 |  |  | 2 | Medium | FALSE | TRUE | 0
2026-07-03 | 10340145 | 2330515 | Dev Team B | VÕ BẢO MINH | Backlog | 0 | Todo | Low | Q3 | 2026Q3 | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 10340143 | 2415056 | Dev Team B | VÕ BẢO MINH | Discuss Req | 1 | Doing | Low | Q3 | 2026Q3 | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10340127 | 2425861 | Dev Team B | VÕ BẢO MINH | Backlog | 0 | Todo | Low | Q3 | 2026Q3 | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 10340024 | 2426812 | Dev Team B | VÕ BẢO MINH | Design UI/UX | 2 | Doing | Low | Q3 | 2026Q3 | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10340021 | 2403987 | Dev Team B | VÕ BẢO MINH | Web B Coding | 3 | Doing | Low | Q3 | 2026Q3 | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Medium | FALSE | FALSE | 1
2026-07-03 | 10340020 | 2540233 | Dev Team B | VÕ BẢO MINH | Dev To do | 3 | Todo | Low | Q3 | 2026Q3 | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 1 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 10058431 | 1954732 | Dev Team B | VÕ BẢO MINH | Dev To do | 3 | Todo | Low | Backlog |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 58 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 9956873 | 1923581 | Dev Team B | VÕ BẢO MINH | Pending | 3 | Blocked | Low | Backlog |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 80 |  |  |  | High | TRUE | FALSE | 0
2026-07-03 | 10059258 | 2403987 | Dev Team B | VÕ BẢO MINH | UAT Testing | 5 | UAT | Low | Q2 | 2026Q2 | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 58 |  |  | 1 | Medium | FALSE | TRUE | 1
2026-07-03 | 9956507 | 2275303 | Dev Team B | VÕ BẢO MINH | Ready for go-live | 6 | Done | Medium | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 3 | TRUE | FALSE | TRUE | 0 |  | 80 | 21 | 98 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9956961 | 2400155 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Medium | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 2 | TRUE | FALSE | TRUE | 2 |  | 80 | 75 | 77 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10055837 | 2423945 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 59 | 26 | 28 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9956498 | 2154685 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Medium | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 2 | TRUE | FALSE | TRUE | 6 |  | 80 | 85 | 175 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9956496 | 2385402 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 80 | 11 | 29 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9956499 | 2197982 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 80 | 42 | 139 |  | Low | FALSE | FALSE | 1
2026-07-03 | 10334131 | 2506884 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 10334133 | 2526008 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 10209339 | 2482578 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 28 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 10334127 | 2216483 | Team Mobile | VÕ THANH PHONG | Web B Coding | 3 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10334124 | 2540233 | Team Mobile | VÕ THANH PHONG | Discuss Req | 1 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10209283 | 2415056 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 28 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 10334126 | 2310394 | Team Mobile | VÕ THANH PHONG | Waiting FTL | 3 | Blocked | Low | Q3 |  | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | High | TRUE | FALSE | 0
2026-07-03 | 10209368 | 2291957 | Team Mobile | VÕ THANH PHONG | Discuss Req | 1 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 28 |  |  | 2 | Medium | FALSE | TRUE | 0
2026-07-03 | 9953690 | 2397922 | Team Mobile | VÕ THANH PHONG | Dev To do | 3 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 81 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 9739425 | 2317336 | Team Mobile |  | Design review | 2 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 |  |  | 2 | Medium | FALSE | TRUE | 0
2026-07-03 | 9953664 | 2330515 | Team Mobile | VÕ THANH PHONG | Design UI/UX | 2 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 81 |  |  | 2 | Medium | FALSE | TRUE | 0
2026-07-03 | 10334129 | 2438262 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 2 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739426 | 2289280 | Team Mobile |  | Dev To do | 3 | Todo | Low | Q3 |  | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 122 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 9953685 | 2307583 | Team Mobile | VÕ THANH PHONG | Discuss Req | 1 | Todo | Low | Backlog |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 81 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 9953687 | 2376660 | Team Mobile | VÕ THANH PHONG | Backlog | 0 | Todo | Low | Backlog |  | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 81 |  |  | 2 | Low | FALSE | TRUE | 0
2026-07-03 | 9739412 | 2174942 | Team Mobile | VÕ THANH PHONG | Pending | 3 | Blocked | Low | Backlog | 2026Q1 | FALSE | FALSE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 |  |  | 2 | High | TRUE | TRUE | 0
2026-07-03 | 10217565 | 2340654 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 27 | 0 | 96 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090312 | 2310394 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 | 51 | 98 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090329 | 2446191 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 52 | 35 | 40 |  | Low | FALSE | FALSE | 1
2026-07-03 | 10090302 | 2222464 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 | 1 | 152 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090343 | 2443571 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 52 | 24 | 30 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090240 | 2133352 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Medium | Q2 |  | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 | 3 | 205 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090247 | 2246969 | MW Team | NGUYỄN MINH HỮU | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 52 | 3 | 136 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10090293 | 2275303 | MW Team | NGUYỄN MINH HỮU | FTL Coding | 3 | Doing | Medium | Q2 |  | FALSE | FALSE | TRUE | TRUE | 3 | FALSE |  | FALSE | 0 |  | 52 | 51 | 156 |  | Medium | FALSE | FALSE | 0
2026-07-03 | 10090287 | 2216483 | MW Team | NGUYỄN MINH HỮU | Waiting FTL | 3 | Blocked | Low | Q2 |  | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 | 51 | 184 | 0 | High | TRUE | TRUE | 0
2026-07-03 | 10090263 | 2238356 | MW Team | NGUYỄN MINH HỮU | UAT Testing | 5 | UAT | High | Q2 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | Medium | FALSE | TRUE | 0
2026-07-03 | 10090209 | 2084592 | MW Team | NGUYỄN MINH HỮU | Waiting FTL | 3 | Blocked | High | Q2 |  | FALSE | FALSE | FALSE | TRUE | 3 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | High | TRUE | TRUE | 0
2026-07-03 | 10090204 | 2149046 | MW Team | NGUYỄN MINH HỮU | UAT Testing | 5 | UAT | High | Q2 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | Medium | FALSE | TRUE | 0
2026-07-03 | 10090258 | 2106995 | MW Team | NGUYỄN MINH HỮU | UAT Testing | 5 | UAT | Low | Q2 |  | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | Medium | FALSE | TRUE | 0
2026-07-03 | 10090289 | 2283752 | MW Team | NGUYỄN MINH HỮU | UAT Testing | 5 | UAT | Low | Q2 |  | FALSE | FALSE | TRUE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | Medium | FALSE | TRUE | 0
2026-07-03 | 10090323 | 2437753 | MW Team | NGUYỄN MINH HỮU | FSS Eval CR | 1 | Doing | Low | Q3 |  | FALSE | FALSE | TRUE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 52 |  |  | 0 | Medium | FALSE | TRUE | 0
2026-07-03 | 10090283 | 2289280 | MW Team | NGUYỄN MINH HỮU | Discuss Req | 1 | Todo | Low | Backlog |  | FALSE | FALSE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 52 |  |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739429 | 2275303 | Team Mobile |  | Go-live | 7 | Done | Medium | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 3 | TRUE | FALSE | TRUE | 33 |  | 122 | 117 | 153 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9953652 | 2310394 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 81 | 76 | 95 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9953677 | 2400155 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q2 |  | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 81 | 76 | 77 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739428 | 2329940 | Team Mobile |  | Go-live | 7 | Done | Medium | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | TRUE | FALSE | TRUE | 13 |  | 122 | 93 | 102 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9931785 | 2306127 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q2 |  | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 85 | 47 | 71 |  | Low | FALSE | FALSE | 0
2026-07-03 | 10007137 | 2372910 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 70 | 9 | 47 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739424 | 2216483 | Team Mobile |  | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 122 | 61 | 124 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9931751 | 2400512 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 85 | 10 | 14 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739423 | 2222464 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 122 | 47 |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739422 | 2212813 | Team Mobile |  | Go-live | 7 | Done | Low | Q2 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 41 | 61 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739420 | 2133352 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | TRUE | 2 | TRUE | TRUE | FALSE | 0 |  | 122 | 28 | 159 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739418 | 2247969 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | TRUE | TRUE | FALSE | 0 |  | 122 | 19 | 90 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739416 | 2186435 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | TRUE | 2 | TRUE | TRUE | FALSE | 0 |  | 122 | 28 | 125 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739417 | 2285823 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | TRUE | TRUE | FALSE | 0 |  | 122 | 13 | 48 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739421 | 2224919 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | TRUE | TRUE | FALSE | 0 |  | 122 | 18 | 87 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739413 | 2302697 | Team Mobile |  | Rejected | -1 | Rejected | Low | Q1 | 2026Q2 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 2 | 36 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739430 | 2185585 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 102 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739431 | 2154685 | Team Mobile |  | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | TRUE | 2 | FALSE |  | FALSE | 0 |  | 122 | 0 | 112 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739432 |  | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 28 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739433 | 2077975 | Team Mobile |  | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 104 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739434 | 2196774 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 142 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739435 | 2242463 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 |  |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739436 | 2185583 | Team Mobile | VÕ THANH PHONG | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 99 |  | Low | FALSE | FALSE | 0
2026-07-03 | 9739106 | 2213580 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 13 | 88 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739108 | 2186435 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | TRUE | 2 | TRUE | FALSE | TRUE | 0 |  | 122 | 8 | 105 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9739105 | 2065876 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Low | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | FALSE |  | FALSE | 0 |  | 122 | 0 | 174 |  | Low | FALSE | FALSE | 1
2026-07-03 | 9744376 | 1722552 | Dev Team B | VÕ BẢO MINH | Go-live | 7 | Done | Medium | Q1 | 2026Q1 | FALSE | TRUE | FALSE | FALSE | 1 | TRUE | FALSE | TRUE | 18 |  | 121 | 0 | 371 |  | Low | FALSE | FALSE | 0

## dim_task
task_id | request_id | task_name | category | dept_tag | metatype | parent_id | jira_url | owner_division | created_at | start_at | deadline_at | completed_at | cr_received | cr_recommit | last_review | reason | wr_assessment | wr_next
10347513 |  | [Flex.MSP] Hệ thống điện chuyển mạch VSDC | CR |  | Task | 0 |  |  | 2026-07-03 10:21
10274446 | 2129248 | [CR] [2129248] [RMD] Add Special room information for Locations | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-65 | RMD | 2026-06-19 09:39 |  | 2026-06-29 23:59 | 2026-07-02 16:03 | 2025-10-16 | 2026-05-07
10223433 | 2335404 | [CR] [2335404] [RMD] Upgrade the automatic limit adjustment feature on Customer Portal Admin | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-50 | RMD | 2026-06-08 13:50 |  | 2026-06-12 23:59 | 2026-06-12 08:16 | 2026-04-06 | 2026-05-25
10055830 | 2084592 | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-15 | RMD | 2026-05-05 17:37 |  | 2026-05-15 23:59 | 2026-05-16 08:01 | 2025-10-04 | 2026-01-27
9739419 | 2084592 | [CR] [2084592] [RMD] Declare Limit & Type For Account Using Special Product on FLEX system | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-585 | RMD | 2026-03-03 16:39 | 2026-02-02 | 2026-05-31 23:59 |  | 2025-10-04 | 2026-02-11 | 2026-07-01 |  | BA đã gửi mail hỏi next step nhưng RMD không phản hồi | No
9739414 | 2149046 | [CR] [2149046] [IT] EKYC | CR | IT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-710 | IT | 2026-03-03 16:39 |  | 2026-05-22 23:59 |  |  |  | 2026-06-30 |  | VNPT cung cấp SDK và giải pháp chưa đáp ứng được nhu cầu rút gọn hoàn toàn EKYC và quét khuôn mặt | Chờ VNPT đánh giá
9739427 | 2283752 | [CR] [2283752] [SS] Send Notification via Elite App and mail all right issue | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-885 | SS | 2026-03-03 16:40 |  |  |  | 2026-01-27 |  | 2026-07-01 |  | Luồng hệ thống thiếu gọi API đăng ký gói trả phí vào Core | Thảo luận để tìm solution
9739415 | 2238356 | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-685 | SS | 2026-03-03 16:39 | 2026-03-12 | 2026-05-29 23:59 |  | 2025-12-26 |  | 2026-07-01 |  | FSS điều chỉnh công thức theo yêu cầu của MSD | MSD test
9953694 | 2335404 | [CR] [2335404] Upgrade the automatic limit adjustment feature | CR |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1212 | RMD | 2026-04-13 17:22 |  |  |  | 2026-04-06 |  | 2026-07-01 |  | RMD thêm chức năng hiện popup cảnh báo khi hệ thống đang chạy batch | MW code
10340145 | 2330515 | [CR] [2330515] [RMD] IPO Share Subscription Feature | CR | RMD | Task | 0 |  | RMD | 2026-07-02 08:56 |  |  |  | 2026-03-23
10340143 | 2415056 | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | CR | MKT | Task | 0 |  | MKT | 2026-07-02 08:55 |  |  |  | 2026-04-16
10340127 | 2425861 | [CR] [2425861] [RS] Research Portal: Phase 2 | CR | RS | Task | 0 |  | RS | 2026-07-02 08:55 |  |  |  | 2026-04-23
10340024 | 2426812 | [CR] [2426812] [MKT] Merge CCC & RS chatbot into one Master Client Chatbot | CR | MKT | Task | 0 |  | MKT | 2026-07-02 08:44 |  |  |  | 2026-04-24
10340021 | 2403987 | [CR] [2403987] [SS] Loyalty System - Phase 1 | CR | SS | Task | 0 |  | SS | 2026-07-02 08:42 |  |  |  | 2025-12-31 | 2026-05-14
10340020 | 2540233 | [CR] [2540233] [SS] FIFA WORLD CUP CHALLENGE 2026 | CR | SS | Task | 0 |  | SS | 2026-07-02 08:42
10058431 | 1954732 | [CR] [1954732] [HR] HR report automation | CR | HR | Task | 0 |  | HR | 2026-05-06 08:34
9956873 | 1923581 | [CR] [1923581] [RMD] Tool to control the number of positions that need to be closed out | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-17 | RMD | 2026-04-14 09:25
10059258 | 2403987 | [CR] [2403987] [SS] Loyalty System - Phase 1 - Login Screen | CR | SS | Task | 0 |  | SS | 2026-05-06 13:54 |  |  |  | 2025-12-31 | 2026-05-14 | 2026-07-02 |  | Hoàn thành các setup cơ bản cho webadmin và màn hình Login | Bổ sung cơ chế xác thực MFA với Google Authenticator
9956507 | 2275303 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-29 | SS | 2026-04-14 09:17 |  | 2026-05-04 23:59 | 2026-05-05 17:43 | 2026-01-27 | 2026-04-24
9956961 | 2400155 | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | CR | MKT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-39 | MKT | 2026-04-14 09:43 |  | 2026-06-26 23:59 | 2026-06-29 08:17 | 2026-04-13
10055837 | 2423945 | [CR] [2423945] [SS] Enhance the promotional declaration feature on the Admin Portal | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-40 | SS | 2026-05-05 17:48 |  |  | 2026-06-01 08:11 | 2026-05-04
9956498 | 2154685 | [CR] [2154685] [BMD] Upgrade fund certificate trading feature on Mobile app | CR | BMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/FCD-11 | BMD | 2026-04-14 09:15 | 2026-02-09 | 2026-04-28 23:59 | 2026-05-05 14:36 | 2025-11-11 | 2026-01-27
9956496 | 2385402 | [CR] [2385402] [MKT] Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | CR | MKT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-36 | MKT | 2026-04-14 09:15 |  |  | 2026-04-25 09:17 | 2026-03-27 | 2026-04-06
9956499 | 2197982 | [CR] [2197982] [RS] Research Landing Page: All Features & Phase 1 Execution | CR | RS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/RSG-1 | RS | 2026-04-14 09:16 | 2026-03-09 |  | 2026-04-20 08:28 | 2025-12-02 | 2026-02-23
10334131 | 2506884 | [CR] [2506884] [LG] Touchpoint for products | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1438 | LG | 2026-07-01 09:35 |  |  |  | 2026-06-30
10334133 | 2526008 | [CR] [2526008] [LG] Goal-based tool phase 2 and Touchpoint for tool | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1463 | LG | 2026-07-01 09:35 |  |  |  | 2026-06-30
10209339 | 2482578 | [CR] [2482578] [AC] Upgrade the QR Code Deposit Function on the PHS App | CR | AC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1388 | ACC | 2026-06-05 09:49 |  |  |  | 2026-06-01 |  | 2026-07-01 |  | Backlog | No
10334127 | 2216483 | [CR] [2216483] [MSD] Loyalty system on mobile app (phase 2) | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1488 | SS | 2026-07-01 09:34 |  |  |  | 2025-12-31
10334124 | 2540233 | [CR] [2540233] [MSD] FIFA WORLD CUP CHALLENGE 2026 | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1263 | SS | 2026-07-01 09:33 |  |  |  | 2026-06-30
10209283 | 2415056 | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | CR | MKT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1363 | MKT | 2026-06-05 09:47 |  |  |  | 2026-04-16 |  | 2026-07-01 |  | Backlog | No
10334126 | 2310394 | [CR] [2310394] [AC] Tax analysis and estimation tools for investors (phase 2) | CR | AC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1288 | ACC | 2026-07-01 09:33 |  |  |  | 2026-03-26
10209368 | 2291957 | [CR] [2291957] [IC] Update the account opening function on the PHS Elite app login screen | CR | IC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1338 | IC | 2026-06-05 09:54 |  |  |  | 2026-04-17 |  | 2026-07-01 |  | Đúng tiến độ | Review design
9953690 | 2397922 | [CR] [2397922] [LG] Enhance filter for Elite Fund | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1313 | LG | 2026-04-13 17:21 |  |  |  | 2026-04-06 |  | 2026-07-01 |  | Đúng tiến độ | Mobile code
9739425 | 2317336 | [CR] [2317336] [AC] Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | CR | AC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-935 | AC | 2026-03-03 16:40 |  |  |  | 2026-02-24 |  | 2026-07-01 |  | Đúng tiến độ | Trình CR
9953664 | 2330515 | [CR] [2330515] [RMD] IPO Share Subscription Feature | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1087 | RMD | 2026-04-13 17:11 |  |  |  | 2026-03-23 |  | 2026-07-01 |  | Chờ RMD confirm nghiệp vụ | Review design
10334129 | 2438262 | [CR] [2438262] [LG]_Goal-based Tool | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1413 | LG | 2026-07-01 09:34 |  |  |  | 2026-05-11
9739426 | 2289280 | [CR] [2289280] [FN] Future-Dated Withdrawal Scheduling for Customers | CR | FN | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-910 | FN | 2026-03-03 16:40 |  |  |  | 2026-01-30 |  | 2026-07-01 |  | Theo đúng tiến độ | MW code
9953685 | 2307583 | [CR] [2307583] [LG] PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1137 | LG | 2026-04-13 17:18 |  |  |  | 2026-03-16 |  | 2026-07-01 |  | Đang thiết kế tổng thể lại cho FE, BE | No
9953687 | 2376660 | [CR] [2376660] [CCC] Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | CR | CCC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1162 | SS | 2026-04-13 17:20 |  |  |  | 2026-03-27 |  | 2026-07-01 |  | Không có thông tin về action tiếp theo | No
9739412 | 2174942 | [CR] [2174942] [MSD] Automation Test Proposal | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-960 | SS | 2026-03-03 16:39 |  |  |  | 2026-01-25 |  | 2026-07-01 |  | Pending | No
10217565 | 2340654 | [CR] [2340654] [FN] [No.02-2026] Updated payment order form of IVB | CR | FN | Task | 0 |  | FN | 2026-06-06 15:54 |  |  | 2026-06-06 15:56 | 2026-03-02
10090312 | 2310394 | [CR] [2310394 - 2391899] [KT] [No.01-2026] Tax analysis and estimation tools for investors. | CR | KT | Task | 0 |  | ACC | 2026-05-12 09:03 |  |  | 2026-07-02 16:50 | 2026-03-26
10090329 | 2446191 | [CR] [2446191] [MSD] [No.08-2026] VCF0051 – Adjust Report Extraction Conditions | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-249 | SS | 2026-05-12 09:09 |  |  | 2026-06-16 10:25 | 2026-05-07 | 2026-05-22
10090302 | 2222464 | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-137 | RMD | 2026-05-12 09:00 |  |  | 2026-05-13 10:27 | 2025-12-12
10090343 | 2443571 | [CR] [2443571] [SS] [No.09-2026] Restrict using PHS email address for securities transactions | CR | SS | Task | 0 |  | SS | 2026-05-12 09:14 |  |  | 2026-06-05 11:06 | 2026-05-06
10090240 | 2133352 | [CR] [2133352] [RMD] [No.12-2025] Margin product calculation tool | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-9 | RMD | 2026-05-12 08:43 |  |  | 2026-05-15 10:32 | 2025-10-22
10090247 | 2246969 | [CR] [2246969] [DTD] [No.39-2025] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | CR | DTD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-10 | DTD | 2026-05-12 08:45 |  |  | 2026-05-15 10:32 | 2025-12-30
10090293 | 2275303 | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository features via the PHS Elite Trading application | CR | DTD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-12 | SS | 2026-05-12 08:57 |  |  | 2026-07-02 16:49 | 2026-01-27
10090287 | 2216483 | [CR] [2216483] [MSD] [No.33-2025] Loyalty Customer System (Core Flex) | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/projects/PPM/issues/PPM-230 | MSD | 2026-05-12 08:55 |  |  | 2026-07-03 08:46 | 2025-12-31 |  | 2026-07-03 |  | đã golive Flex trước, xong phase 1 | Đợi team B dựng base
10090263 | 2238356 | [CR] [2238356] [MSD] [No.27-2025]ADVANCE MARGIN FOR DERIVATIVES | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-11 | MSD | 2026-05-12 08:52 |  |  |  | 2025-12-26 |  | 2026-07-03 |  | Công thức mới, đợi SS và RMD bàn giao công thức (06/07/2026) | No action
10090209 | 2084592 | [CR] [2084592] [RMD] [No.10-2025] Calculate interest for accounts using special interest rate products | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-6 | RMD | 2026-05-12 08:33 |  |  |  | 2025-10-04 |  | 2026-07-03 |  | Đang không tự động chuyển loại hình được, Core đang xử lý cho CR này bằng cách replace lại loại hình hiện tại. Nghiệp vụ mong muốn phải có loại hình mới rồi chuyển sang. Nghiệp vụ nói nếu không có phần này CR sẽ không golive được. CR đang cần nghiệp vụ(RMD) và core trao đổi lại để chốt phương án. | Push RMD chốt phương án
10090204 | 2149046 | [CR] [2149046] [SS] [No.28-2025] Adjustment of the account opening flow on the PHS ELITE TRADING application | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-5 | SS | 2026-05-12 08:31 |  |  |  | 2025-11-12 |  | 2026-07-03 |  | Stuck tại VNPT | Push VNPT
10090258 | 2106995 | [CR] [2106995] [DTD] [No.25-2025] Add put-through order trading feature on PHS ELITE XPRO | CR | DTD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-94 | DTD | 2026-05-12 08:50 |  |  |  | 2025-10-08 |  | 2026-07-03 |  | Còn case cảnh báo lệnh ngoài giờ với cả xác nhận lệnh 2F của nđt nước ngoài Sở nghỉ sớm Sở chuẩn bị mừng 50 năm thành phố mang tên bác | Đợi sở mở đợt test tiếp theo
10090289 | 2283752 | [CR] [2283752] [DTD] [No.03-2026] Send Notification via Elite App and mail all right issue | CR | DTD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-133 | DTD | 2026-05-12 08:56 |  |  |  | 2026-01-27 |  | 2026-07-03 |  | Phát sinh case tài khoản phải kích hoạt nhận SMS trả phí + hiện tại, mobile chỉ gọi api để đăng kí nhận template trả phí trong khi tài khoản chưa kích hoạt + đang nghiệp vụ đang test lại luồng đăng kí sms template cũ để verify có được trả phí hay chưa | Push nghiệp vụ test MW đánh giá xử lý case kích hoạt sms trả phí nếu khách hàng chưa kích hoạt
10090323 | 2437753 | [CR] [2437753] [SS] [No.07-2026] AF & LN Duplication & Bulk Import Function | CR | SS | Task | 0 |  |  | 2026-05-12 09:08 | [5 empty] | 2026-07-03 |  | Về CR.No.07.2026-MSD, do việc quản lý version hiện đang khá phức tạp và phần lớn các CR tại môi trường UAT chưa được Golive, nên ở thời điểm hiện tại phía FSS chưa thể triển khai phát triển CR này. Theo kế hoạch Golive gần nhất, FSS dự kiến có thể bàn giao UAT vào ngày 31/08/2026. | chuyển sang quý 3
10090283 | 2289280 | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling for Customers | CR | FN | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PPM-191 | FN | 2026-05-12 08:53 |  |  |  | 2026-01-30
9739429 | 2275303 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-835 | SS | 2026-03-03 16:40 |  | 2026-05-26 23:59 | 2026-06-29 14:10 | 2026-01-27
9953652 | 2310394 | [CR] [2310394] Tax analysis and estimation tools for investors (Phase 1) | CR |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1062 | ACC | 2026-04-13 17:05 |  |  | 2026-06-29 14:09 | 2026-03-26
9953677 | 2400155 | [CR] [2400155] Marketing - Develop Mission Tracking Page for Promotion Q1.2026 | CR |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1112 | MKT | 2026-04-13 17:14 |  |  | 2026-06-29 14:09 | 2026-04-13
9739428 | 2329940 | [CR] [2329940] [RS] AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | CR | RS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-860 | RS | 2026-03-03 16:40 |  | 2026-05-22 23:59 | 2026-06-05 09:44 | 2026-02-23
9931785 | 2306127 | [CR] [2306127] INB_ Proposal to implement the mobile app notifications for Elite Seeds | CR |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1037 | INB | 2026-04-09 17:00 |  |  | 2026-05-27 13:29 | 2026-03-17
10007137 | 2372910 | [CR][2372910] [RESEARCH] Permission to get API data from OpenAcc web | CR |  | Task | 0 |  | RS | 2026-04-24 09:27 |  |  | 2026-05-04 08:26 | 2026-03-18
9739424 | 2216483 | [CR] [2216483] [MSD] LOYALTY SYSTEM ON MOBILE APP | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-760 | SS | 2026-03-03 16:39 |  |  | 2026-05-04 08:15 | 2025-12-31
9931751 | 2400512 | [SDK] [2400512] Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google | SDK |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-1012 | IT | 2026-04-09 16:57 |  |  | 2026-04-20 08:12 | 2026-04-06
9739423 | 2222464 | [CR] [2222464] [RMD] Add sign-in method | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-785 | RMD | 2026-03-03 16:39 |  |  | 2026-04-20 08:11
9739422 | 2212813 | [CR] [2212813] [SS] Derivatives Order Placement UI Enhancement | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-810 | SS | 2026-03-03 16:39 |  |  | 2026-04-13 17:02 | 2026-02-11
9739420 | 2133352 | [CR] [2133352] [RMD] Margin product calculation tool | CR | RMD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-560 | RMD | 2026-03-03 16:39 | 2026-03-02 | 2026-03-30 23:59 | 2026-03-30 15:00 | 2025-10-22
9739418 | 2247969 | [CR] [2247969] [SS] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-610 | SS | 2026-03-03 16:39 | 2026-03-11 | 2026-03-30 23:59 | 2026-03-30 15:00 | 2025-12-30 | 2026-02-27
9739416 | 2186435 | [CR] [2186435] [MSD] PROMOTION REGISTRATION FUNCTION UPGRADE | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-660 | SS | 2026-03-03 16:39 | 2026-03-02 | 2026-03-30 23:59 | 2026-03-30 14:59 | 2025-11-25 | 2026-02-03
9739417 | 2285823 | [CR] [2285823] [IC] THE LOGIN SCREEN GREETING MESSAGE | CR | IC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-635 | IC | 2026-03-03 16:39 | 2026-03-03 | 2026-03-16 23:59 | 2026-03-16 11:11 | 2026-01-27 | 2026-03-02
9739421 | 2224919 | [CR] [2224919] [SS] Feature to save multiple login accounts on a single device in the PHS Elite Trading app | CR | SS | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-535 | SS | 2026-03-03 16:39 | 2026-02-26 | 2026-03-16 23:59 | 2026-03-16 11:10 | 2025-12-19
9739413 | 2302697 | [CR] [2302697] [LG] Add content regarding personal data protection | CR | LG | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-735 | LG | 2026-03-03 16:39 |  |  | 2026-03-06 08:59 | 2026-01-29
9739430 | 2185585 | [CR] [2185585] [IT] Add the Reward Redemption feature to the PHS Elite Trading application | CR | IT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-510 | IT | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2025-11-21 | 2026-02-11
9739431 | 2154685 | [CR] [2154685] [INB] Mutual Fund Distribution (Phase 2) | CR | INB | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-485 | INB | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2025-11-11 | 2025-12-10
9739432 |  | [MKT] Update Logo PHS 20 years anniversary | Internal |  | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-460 | MKT | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2026-02-03
9739433 | 2077975 | [CR] [2077975] [MKT] Collaboration with Woori Bank Proposal | CR | MKT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-435 | MKT | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2025-11-19
9739434 | 2196774 | [CR] [2196774] [INB] Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | CR | INB | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-410 | INB | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2025-10-12
9739435 | 2242463 | [CR] [2242463] [MSD] PROMOTION: HORSE YEAR FORTUNE 2026 | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-385 | SS | 2026-03-03 16:40 |  |  | 2026-03-03 16:41
9739436 | 2185583 | [CR] [2185583] [IT] Enhancement of the Smart OTP Function on the PHS Elite Trading Application | CR | IT | Task | 0 | https://dev-ftl-jira.phs.vn/browse/MEA-360 | IT | 2026-03-03 16:40 |  |  | 2026-03-03 16:41 | 2025-11-24
9739106 | 2213580 | [CR] [2213580] [CCC] Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | CR | CCC | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-3 | CCC | 2026-03-03 15:47 |  |  | 2026-03-17 10:52 | 2025-12-19 | 2026-01-20
9739108 | 2186435 | [CR] [2186435] [MSD] Enhance Promotion features on Admin Customer Portal | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-12 | MSD | 2026-03-03 15:47 | 2026-03-02 | 2026-03-09 23:59 | 2026-03-10 08:47 | 2025-11-25 | 2026-01-22
9739105 | 2065876 | [CR] [2065876] [MSD] Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | CR | MSD | Task | 0 | https://dev-ftl-jira.phs.vn/browse/PP-1 | MSD | 2026-03-03 15:46 |  |  | 2026-03-04 06:56 | 2025-09-11 | 2025-11-24
9744376 | 1722552 | [CR] [1722552] [BMD] Provide API data source for Transaction fluctuation function in Broker portal | CR | BMD | Task | 0 |  | BMD | 2026-03-04 16:25 |  | 2026-02-13 23:59 | 2026-03-04 16:29 | 2025-02-26

## dim_team
team | lead_email
Team Mobile | phongvo@phs.vn
Dev Team B | minhvo@phs.vn
MW Team | huunguyen@phs.vn

## dim_stage
stage | stage_order | status_group
Rejected | -1 | Rejected
Backlog | 0 | Todo
Discuss Req | 1 | Doing
FSS Eval CR | 1 | Doing
Design UI/UX | 2 | Doing
Design review | 2 | Doing
Dev To do | 3 | Todo
FTL Coding | 3 | Doing
Web B Coding | 3 | Doing
Waiting FTL | 3 | Blocked
Pending | 3 | Blocked
UAT Testing | 5 | UAT
Ready for go-live | 6 | Done
Go-live | 7 | Done

## bridge_task_division
task_id | division
10274446 | RMD
10223433 | RMD
10223433 | IT
10055830 | RMD
10055830 | IT
9739419 | IT
9739419 | SS
9739414 | IT
9739414 | SS
9739414 | LG
9739414 | IC
9739427 | IT
9739415 | IT
9739415 | SS
9953694 | SS
10340145 | RMD
10340145 | IT
10340143 | MKT
10340143 | IT
10340127 | RS
10340127 | IT
10340024 | RS
10340024 | MKT
10340024 | CCC
10340021 | SS
10340021 | MKT
10340021 | IT
10340021 | CCC
10340020 | SS
10340020 | IT
10058431 | HR
10058431 | IT
9956873 | BMD
10059258 | SS
10059258 | MKT
10059258 | IT
10059258 | CCC
9956507 | IT
9956961 | MKT
9956961 | IT
10055837 | SS
9956498 | SS
9956498 | BMD
9956498 | FN
9956498 | IT
9956498 | MSD
9956496 | MKT
9956496 | IT
9956499 | RS
9956499 | IT
10334131 | IT
10334133 | IT
10209339 | IT
10334127 | IT
10334124 | IT
10209283 | IT
10334126 | IT
10209368 | IT
9953690 | SS
9739425 | IT
9739425 | SS
9953664 | SS
10334129 | IT
9739426 | IT
9739426 | SS
9953685 | SS
9953687 | SS
9953687 | LG
9953687 | IT
9953687 | CCC
9739412 | IT
10090302 | SS
10090240 | SS
10090247 | SS
10090287 | SS
10090263 | SS
10090209 | SS
10090204 | SS
10090258 | SS
10090289 | SS
10090283 | FN
9739429 | IT
9953652 | SS
9739428 | IT
9739428 | SS
9931785 | SS
9931785 | IC
9931785 | MSD
10007137 | IT
9739424 | IT
9739423 | IT
9739423 | SS
9739422 | IT
9739420 | IT
9739420 | SS
9739418 | IT
9739416 | IT
9739417 | IT
9739421 | IT
9739413 | IT
9739413 | SS
9739430 | SS
9739430 | CCC
9739430 | MKT
9739431 | IT
9739431 | SS
9739431 | FN
9739432 | IT
9739433 | IT
9739433 | SS
9739433 | HR
9739433 | BMD
9739434 | IT
9739434 | SS
9739434 | FN
9739435 | IT
9739436 | SS
9739106 | CCC
9739108 | IT
9739108 | MSD
9739105 | IT
9739105 | MSD
9744376 | IT

## bridge_task_platform
task_id | platform
10274446 | Broker Portal
10223433 | Elite App
10223433 | Customer Portal
10055830 | Broker Portal
9739419 | Elite App
9739414 | Elite App
9739427 | Elite App
9739415 | Elite App
9953694 | Elite App
10340145 | Customer Portal
10340143 | Elite App
10340143 | Customer Portal
10340127 | Research Portal
10340024 | PHS Website
10340020 | Customer Portal
10058431 | Broker Portal
9956873 | Broker Portal
9956507 | Elite App
9956507 | Customer Portal
9956961 | Elite App
9956961 | Customer Portal
10055837 | Customer Portal
9956498 | Fund
9956496 | PHS Website
9956499 | Research Portal
10334131 | Elite App
10334131 | Xpro
10334133 | Elite App
10334133 | Xpro
10209339 | Elite App
10334127 | Elite App
10334124 | Elite App
10209283 | Elite App
10334126 | Elite App
10209368 | Elite App
9953690 | Elite App
9739425 | Elite App
9953664 | Elite App
10334129 | Elite App
10334129 | Xpro
9739426 | Elite App
9953685 | Elite App
9953687 | Elite App
9739412 | Elite App
10217565 | Flex
10090312 | Elite App
10090329 | Flex
10090302 | App-MW
10090343 | Elite App
10090240 | Elite App
10090247 | Elite App
10090293 | Elite App
10090287 | Elite App
10090287 | Customer Portal
10090263 | Elite App
10090209 | App-MW
10090204 | Elite App
10090258 | Xpro
10090289 | Elite App
10090283 | Elite App
9739429 | Elite App
9953652 | Elite App
9953677 | Elite App
9739428 | Elite App
9931785 | Elite App
9931785 | Xpro
10007137 | Elite App
9739424 | Elite App
9931751 | Elite App
9739423 | Elite App
9739422 | Elite App
9739420 | Elite App
9739418 | Elite App
9739416 | Elite App
9739417 | Elite App
9739421 | Elite App
9739413 | Elite App
9739430 | Elite App
9739431 | Elite App
9739432 | Elite App
9739433 | Elite App
9739434 | Elite App
9739435 | Elite App
9739436 | Elite App
9739106 | Customer Portal
9739108 | Customer Portal
9739105 | Customer Portal
9744376 | Broker Portal

## bridge_task_devunit
task_id | devunit
10274446 | Web B
10223433 | FTL
10223433 | Mobile
10223433 | Web B
10055830 | MW
10055830 | Web B
9739419 | FTL
9739419 | FSS
9739419 | MW
9739419 | Mobile
9739419 | Web B
9739427 | FTL
9739427 | FSS
9739427 | MW
9739427 | Mobile
10340145 | MW
10340145 | Web B
10340143 | Mobile
10340143 | Web B
10340127 | Web B
10340024 | Web B
10340021 | MW
10340021 | Mobile
10340021 | Web B
10058431 | Web B
9956873 | Web B
10059258 | MW
10059258 | Mobile
10059258 | Web B
9956507 | MW
9956961 | MW
9956961 | Web B
10055837 | Web B
9956498 | MW
9956498 | Web B
9956496 | Web B
9956499 | MW
9956499 | Web B
9739425 | FTL
9739425 | FSS
9739425 | MW
9739425 | Mobile
9739426 | FTL
9739426 | FSS
9739426 | MW
9739426 | Mobile
9739412 | MW
9739412 | Mobile
9739429 | FTL
9739429 | MW
9739429 | Mobile
9739428 | FTL
9739428 | MW
9739428 | Mobile
9739424 | FTL
9739424 | FSS
9739424 | MW
9739424 | Mobile
9739424 | Web B
9931751 | Mobile
9739423 | FTL
9739423 | MW
9739423 | Mobile
9739423 | Web A
9739422 | Mobile
9739420 | FTL
9739420 | MW
9739420 | Mobile
9739418 | FTL
9739418 | MW
9739418 | Mobile
9739416 | FTL
9739416 | MW
9739416 | Mobile
9739416 | Web B
9739417 | Mobile
9739421 | Mobile
9739430 | FTL
9739430 | MW
9739430 | Mobile
9739430 | Web B
9739431 | FTL
9739431 | MW
9739431 | Mobile
9739431 | Web B
9739432 | Mobile
9739433 | FTL
9739433 | MW
9739433 | Mobile
9739434 | FTL
9739434 | FSS
9739434 | MW
9739434 | Mobile
9739434 | Web A
9739435 | Mobile
9739435 | Web A
9739436 | Mobile
9739106 | Web B
9739108 | Web B
9739105 | Web B
9744376 | Web B