## Task Tracker
IT Department — Cross-Team Task Tracker 2026
Request ID | Task ID | Task Name | Team | Category | Dept Tag | Priority | Status | Phase | Assignee | Team Lead | Created Date | Deadline | Completed Date | Dependencies | Notes
2275303 | 9739429 | [CR] [2275303] [SS] Enhance securities depository — Mobile UI | Team Mobile | CR | SS | High | Overdue | Q2 | mobile_dev_1 | phongvo@phs.vn | 03/03/2026 | 26/05/2026 |  | 2275303 | Waiting for MW API
2275303 | 9956507 | [CR] [2275303] [SS] Enhance securities depository — Web Admin | Dev Team B | CR | SS | High | Done | Q2 | devb_dev_1 | minhvo@phs.vn | 14/04/2026 | 04/05/2026 | 05/05/2026 | 2275303
2275303 | 10090293 | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository — Middleware API | MW Team | CR | DTD | High | Doing | Q2 | mw_dev_1 | huunguyen@phs.vn | 12/05/2026 |  |  |  | Upstream dependency for Mobile
2084592 | 9739419 | [CR] [2084592] [RMD] Special interest rate on FLEX — Mobile UI | Team Mobile | CR | RMD | Critical | Overdue | Q2 | mobile_dev_2 | phongvo@phs.vn | 03/03/2026 | 31/05/2026 |  | 2084592 | Blocked by 3rd-party FLEX
2084592 | 9956972 | [CR] [2084592] [RMD] Special interest rate — Web Portal | Dev Team B | CR | RMD | Critical | Doing | Q2 | devb_dev_2 | minhvo@phs.vn | 14/04/2026 |  |  | 2084592 | Needs deadline
2084592 | 10090209 | [CR] [2084592] [RMD] [No.10-2025] Special interest rate — Middleware | MW Team | CR | RMD | Critical | Doing | Q2 | mw_dev_2 | huunguyen@phs.vn | 12/05/2026 |  |  |  | Carryover from 2025
2400155 | 9953677 | [CR] [2400155] [MKT] Mission Tracking Page — Mobile App | Team Mobile | CR | MKT | Medium | Doing | Q2 | mobile_dev_3 | phongvo@phs.vn | 13/04/2026 | 20/06/2026 |  | 2400155
2400155 | 9956961 | [CR] [2400155] [MKT] Mission Tracking Page — Web Backend | Dev Team B | CR | MKT | Medium | Doing | Q2 | devb_dev_1 | minhvo@phs.vn | 14/04/2026 |  |  | 2400155 | Needs deadline
2149046 | 9739414 | [CR] [2149046] [IT] EKYC | Team Mobile | CR | IT | Critical | Overdue | Q2 | mobile_dev_1 | phongvo@phs.vn | 03/03/2026 | 22/05/2026 |  |  | EKYC vendor dependency
2329940 | 9739428 | [CR] [2329940] [RS] AI Chatbot Integration | Team Mobile | CR | RS | High | Overdue | Q2 | TBD | phongvo@phs.vn | 03/03/2026 | 22/05/2026 |  |  | Depends on RS team API
2238356 | 9739415 | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | Team Mobile | CR | MSD | High | Overdue | Q2 | TBD | phongvo@phs.vn | 03/03/2026 | 29/05/2026
2222464 | 10090302 | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | MW Team | CR | RMD | Medium | Done | Q2 | mw_dev_1 | huunguyen@phs.vn | 12/05/2026 |  | 13/05/2026
2397922 | 9953690 | [CR] [2397922] Enhance filter for Elite Fund | Team Mobile | CR |  | Low | Todo | Backlog | TBD | phongvo@phs.vn | 13/04/2026 |  |  |  | Needs priority & deadline
1954732 | 10058431 | [CR] [1954732] [HR] HR report automation | Dev Team B | CR | HR | Low | Todo | Backlog | TBD | minhvo@phs.vn | 06/05/2026
2289280 | 10090283 | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling | MW Team | CR | FN | Medium | Todo | Backlog | TBD | huunguyen@phs.vn | 12/05/2026