## Tasks (01012026-05062026)
Tên công việc | Người giao việc | Người thực hiện | Người theo dõi | Khẩn cấp | Quan trọng | Danh sách nhãn | Ngày bắt đầu | Thời hạn | Hoàn thành thực tế | Mô tả công việc | Trạng thái | Kết quả công việc | Mục tiêu | Project Owner | Owner division | Stage | Platform | Related divisions | Q-KPI | Detail | CR 1 | CR 2 | Dev in charge | Reason / Condition | Ngày tạo | Mã công việc (ID) | Mã công việc cha (ID) | Metatype | Họ và tên người nhận việc | Họ và tên người giao việc
CRs in Coding:
[CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | MKT | FTL Coding | Elite App, Customer Portal | MKT, IT |  | https://dev-ftl-jira.phs.vn/browse/PP-39 | 13/04/2026 | 14/05/2026 | MW, Web B |  | 01/06/2026 08:13 | 10186512 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  |  | 15/05/2026 23:59 | 16/05/2026 08:01 |  | Hoàn thành muộn |  |  | Team B | RMD | UAT Testing | Broker Portal | RMD, IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-15 | 04/10/2025 | 27/01/2026 | MW, Web B |  | 05/05/2026 17:37 | 10055830 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  |  | 04/05/2026 23:59 | 05/05/2026 17:42 |  | Hoàn thành muộn |  |  | Team B | SS | UAT Testing | Elite App, Customer Portal | SS, IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-29 | 27/01/2026 | 24/04/2026 | MW |  | 13/04/2026 22:08 | 9953933 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | phongvo2440 |  | phongvo2440 |  |  |  |  | 26/05/2026 23:59 |  |  | Quá hạn |  |  | Mobile Team | SS | UAT Testing | Elite App | IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-835 | 27/01/2026 |  | FTL, MW, Mobile |  | 03/03/2026 16:40 | 9739429 | 0 | Task |  | VÕ THANH PHONG
[CR] [2084592] [RMD] Declare Limit & Type For Account Using Special Product on FLEX system | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 02/02/2026 00:00 | 31/05/2026 23:59 |  |  | Quá hạn |  |  | Mobile Team | RMD | UAT Testing | Elite App | IT, SS | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-585 | 04/10/2025 | 11/02/2026 | FTL, FSS, MW, Mobile, Web B | - FSS needs 23 mandays to implement. - FSS will deliver the code on 24/04. - FTL,Team B and the Mobile Team will need time for integration. - The releated divisions also need time to test before go-live. | 03/03/2026 16:39 | 9739419 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
# Handle API in MW | tuanle0095 | dungnguyenvan2476 | dungnguyenvan2476, tuanle0095 | [7 empty] | Đang làm |  |  | MW Team | IT | UAT Testing | App-MW | IT, MSD |  |  |  |  | MW |  | 25/03/2026 17:47 | 9851085 | 9739419 | Subtask | NGUYỄN VĂN TIẾN DŨNG | LÊ MINH TUẤN
[CR] [2149046] [IT] EKYC | phongvo2440 |  | phongvo2440 |  |  |  |  | 22/05/2026 23:59 |  |  | Quá hạn |  |  | Mobile Team | IT | UAT Testing | Elite App | IT, SS, LG, IC | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-710 |  |  |  | - FTL and FSS will deliver the code on 12/03. - The Mobile Team needs time to integrate the full eKYC, e-contract, and e-signature flow. - Due to the project’s complexity, the relevant departments need at least 3 weeks for testing. - Estimated internal go-live: after 06/04. | 03/03/2026 16:39 | 9739414 | 0 | Task |  | VÕ THANH PHONG
[CR] [2283752] [SS] Send Notification via Elite App and mail all right issue | phongvo2440 |  | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | SS | UAT Testing | Elite App | IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-885 | 27/01/2026 |  | FTL, FSS, MW, Mobile |  | 03/03/2026 16:40 | 9739427 | 0 | Task |  | VÕ THANH PHONG
[CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 12/03/2026 00:00 | 29/05/2026 23:59 |  |  | Quá hạn |  |  | Mobile Team | SS | UAT Testing | Elite App | IT, SS | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-685 |  |  |  | - It requires 26 mandays for development (FSS: 17, FTL + MW: 6, Mobile: 10) and 10 mandays for testing. - CR round 2 has not been approved yet. | 03/03/2026 16:39 | 9739415 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2335404] Upgrade the automatic limit adjustment feature | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | RMD | Web B Coding | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-1212 | 06/04/2026 |  |  |  | 13/04/2026 17:22 | 9953694 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2400155] Marketing - Develop Mission Tracking Page for Promotion Q1.2026 | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | MKT | Web B Coding | Elite App |  |  | https://dev-ftl-jira.phs.vn/browse/MEA-1112 | 13/04/2026 |  |  |  | 13/04/2026 17:14 | 9953677 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2310394] Tax analysis and estimation tools for investors (Phase 1) | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | ACC | Dev To do | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-1062 | 26/03/2026 |  |  |  | 13/04/2026 17:05 | 9953652 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
Dev Team B - Q2:
[CR] [2335404] [RMD] Upgrade the automatic limit adjustment feature on Customer Portal Admin | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  |  | 12/06/2026 23:59 |  |  | Đang làm |  |  | Team B | RMD | FTL Coding | Elite App, Customer Portal | RMD, IT | 2026Q2 |  | 06/04/2026 | 25/05/2026 | FTL, Mobile, Web B |  | 03/06/2026 13:38 | 10198123 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | MKT | FTL Coding | Elite App, Customer Portal | MKT, IT |  | https://dev-ftl-jira.phs.vn/browse/PP-39 | 13/04/2026 |  | MW, Web B |  | 14/04/2026 09:43 | 9956961 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2403987] [SS] Loyalty System - Phase 1 | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | SS | Dev To do |  | SS, MKT, IT, CCC |  |  | 31/12/2025 |  | MW, Mobile, Web B |  | 06/05/2026 13:54 | 10059258 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2129248] [RMD] Add Special room information for Locations | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | RMD | Dev To do | Broker Portal | RMD |  | https://dev-ftl-jira.phs.vn/browse/PP-24 |  |  | Web B |  | 14/04/2026 09:18 | 9956514 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | RMD | UAT Testing | Broker Portal | RMD | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-15 | 04/10/2025 |  | Web B |  | 14/04/2026 09:44 | 9956972 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  |  | 04/05/2026 23:59 | 05/05/2026 17:43 |  | Hoàn thành muộn |  |  | Team B | SS | UAT Testing | Elite App, Customer Portal | IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-29 | 27/01/2026 | 24/04/2026 | MW |  | 14/04/2026 09:17 | 9956507 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2423945] [SS] Enhance the promotional declaration feature on the Admin Portal | minhvo2565 | minhvo2565 | minhvo2565 | [5 empty] | 01/06/2026 08:11 |  | Hoàn thành |  |  | Team B | SS | Go-live | Customer Portal | SS | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-40 | 04/05/2026 |  | Web B |  | 05/05/2026 17:48 | 10055837 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2154685] [BMD] Upgrade fund certificate trading feature on Mobile app | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  | 09/02/2026 00:00 | 28/04/2026 23:59 | 05/05/2026 14:36 |  | Hoàn thành muộn |  |  | Team B | BMD | Go-live | Fund | SS, BMD, FN, IT, MSD | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/FCD-11 | 11/11/2025 | 27/01/2026 | MW, Web B |  | 14/04/2026 09:15 | 9956498 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2385402] [MKT] Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | minhvo2565 | minhvo2565 | minhvo2565 | [5 empty] | 25/04/2026 09:17 |  | Hoàn thành |  |  | Team B | MKT | Go-live | PHS Website | MKT, IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/PP-36 | 27/03/2026 | 06/04/2026 | Web B |  | 14/04/2026 09:15 | 9956496 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2197982] [RS] Research Landing Page: All Features & Phase 1 Execution | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  | 09/03/2026 00:00 |  | 20/04/2026 08:28 |  | Hoàn thành |  |  | Team B | RS | Go-live | Research Portal | RS, IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/RSG-1 | 02/12/2025 | 23/02/2026 | MW, Web B |  | 14/04/2026 09:16 | 9956499 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
Dev Team B - Backlog:
[CR] [1954732] [HR] HR report automation | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | HR | Dev To do | Broker Portal | HR, IT |  |  |  |  | Web B |  | 06/05/2026 08:34 | 10058431 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2426812] [MKT] Merge CCC & RS chatbot into one Master Client Chatbot | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | MKT | Design UI/UX | PHS Website | RS, MKT, CCC |  |  | 24/04/2026 |  | Web B |  | 06/05/2026 08:31 | 10058420 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | MKT | Discuss Req | Elite App, Customer Portal | MKT, IT |  |  | 16/04/2026 |  | Mobile, Web B |  | 06/05/2026 08:40 | 10058445 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2330515] [RMD] IPO Share Subscription Feature | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | RMD | Backlog | Customer Portal | RMD, IT |  |  | 23/03/2026 |  | MW, Web B |  | 06/05/2026 08:36 | 10058441 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2425861] [RS] Research Portal: Phase 2 | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | RS | Backlog | Research Portal | RS, IT |  |  | 23/04/2026 |  | Web B |  | 06/05/2026 08:43 | 10058456 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [1923581] [RMD] Tool to control the number of positions that need to be closed out | minhvo2565 | minhvo2565 | minhvo2565 | [7 empty] | Đang làm |  |  | Team B | RMD | Pending | Broker Portal | BMD |  | https://dev-ftl-jira.phs.vn/browse/PP-17 |  |  | Web B |  | 14/04/2026 09:25 | 9956873 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
Team Mobile - Q2:
[CR] [2329940] [RS] AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | phongvo2440 |  | phongvo2440 |  |  |  |  | 22/05/2026 23:59 | 05/06/2026 09:44 |  | Hoàn thành muộn |  |  | Mobile Team | RS | Ready for go-live | Elite App | IT, SS | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-860 | 23/02/2026 |  | FTL, MW, Mobile |  | 03/03/2026 16:40 | 9739428 | 0 | Task |  | VÕ THANH PHONG
[CR] [2306127] INB_ Proposal to implement the mobile app notifications for Elite Seeds | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 27/05/2026 13:29 |  | Hoàn thành |  |  | Mobile Team | INB | Backlog | Elite App, Xpro | SS, IC, MSD |  | https://dev-ftl-jira.phs.vn/browse/MEA-1037 | 17/03/2026 |  |  |  | 09/04/2026 17:00 | 9931785 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR][2372910] [RESEARCH] Permission to get API data from OpenAcc web | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 04/05/2026 08:26 |  | Hoàn thành |  |  | Data Team | RS | Go-live | Elite App | IT | 2026Q2 |  | 18/03/2026 |  |  |  | 24/04/2026 09:27 | 10007137 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2216483] [MSD] LOYALTY SYSTEM ON MOBILE APP | phongvo2440 |  | phongvo2440 | [5 empty] | 04/05/2026 08:15 |  | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-760 | 31/12/2025 |  | FTL, FSS, MW, Mobile, Web B | Design UI for 4 tiers of customers in Login and Redemption screen | 03/03/2026 16:39 | 9739424 | 0 | Task |  | VÕ THANH PHONG
[SDK] [2400512] Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 20/04/2026 08:12 |  | Hoàn thành |  |  | Mobile Team | IT | Go-live | Elite App |  | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-1012 | 06/04/2026 |  | Mobile |  | 09/04/2026 16:57 | 9931751 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2222464] [RMD] Add sign-in method | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 20/04/2026 08:11 | Link UI/UX: https://www.figma.com/design/uHHmXH1t04o4G3s7huIz6W/Scan-QR-code-to-login?node-id&#61;1-2&amp;t&#61;5c5iWE7ozjoBpWMV-1 | Hoàn thành |  |  | Team A | RMD | Go-live | Elite App | IT, SS | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-785 |  |  | FTL, MW, Mobile, Web A |  | 03/03/2026 16:39 | 9739423 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2212813] [SS] Derivatives Order Placement UI Enhancement | phongvo2440 |  | phongvo2440 | [5 empty] | 13/04/2026 17:02 | UI/UX design: https://www.figma.com/design/zOcqnRjyJHzcj9eB21Y2AO/Derivatives-Order-Placement-UI-Enhancement?node-id&#61;1-2&amp;t&#61;YVhrlDaMrcMz3CVj-1 | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-810 | 11/02/2026 |  | Mobile |  | 03/03/2026 16:39 | 9739422 | 0 | Task |  | VÕ THANH PHONG
Team Mobile - Backlog:
[CR] [2174942] [MSD] Automation Test Proposal | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | SS | Pending | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-960 | 25/01/2026 |  | MW, Mobile |  | 03/03/2026 16:39 | 9739412 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2289280] [FN] Future-Dated Withdrawal Scheduling for Customers | phongvo2440 |  | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | FN | Backlog | Elite App | IT, SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-910 | 30/01/2026 |  | FTL, FSS, MW, Mobile |  | 03/03/2026 16:40 | 9739426 | 0 | Task |  | VÕ THANH PHONG
[CR] [2317336] [AC] Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | phongvo2440 |  | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | AC | Design review | Elite App | IT, SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-935 | 24/02/2026 |  | FTL, FSS, MW, Mobile |  | 03/03/2026 16:40 | 9739425 | 0 | Task |  | VÕ THANH PHONG
[CR] [2307583] PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | LG | Backlog | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-1137 | 16/03/2026 |  |  |  | 13/04/2026 17:18 | 9953685 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2330515] IPO Share Subscription Feature | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | RMD | Design UI/UX | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-1087 | 23/03/2026 |  |  |  | 13/04/2026 17:11 | 9953664 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2376660] Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | SS | Backlog | Elite App |  |  | https://dev-ftl-jira.phs.vn/browse/MEA-1162 | 27/03/2026 |  |  |  | 13/04/2026 17:20 | 9953687 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2397922] Enhance filter for Elite Fund | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | LG | Design UI/UX | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/MEA-1187 | 06/04/2026 |  |  |  | 13/04/2026 17:21 | 9953690 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | MKT | Backlog | Elite App | IT |  |  | 16/04/2026 |  |  |  | 05/06/2026 09:47 | 10209283 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2291957] [IC] Update the account opening function on the PHS Elite app login screen | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | IC | Backlog | Elite App | IT |  |  | 17/04/2026 |  |  |  | 05/06/2026 09:54 | 10209368 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2482578] [AC] Upgrade the QR Code Deposit Function on the PHS App | phongvo2440 | phongvo2440 | phongvo2440 | [7 empty] | Đang làm |  |  | Mobile Team | ACC | Backlog | Elite App | IT |  |  | 01/06/2026 |  |  |  | 05/06/2026 09:49 | 10209339 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
MW Team - Q2:
[CR] [2310394 - 2391899] [KT] [No.01-2026] Tax analysis and estimation tools for investors. | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | ACC | FSS Eval Manday | Elite App |  |  |  | 26/03/2026 |  |  |  | 12/05/2026 09:03 | 10090312 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2446191] [MSD] [No.08-2026] VCF0051 – Adjust Report Extraction Conditions | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | MW Team | SS | UAT Testing | Flex |  |  | https://dev-ftl-jira.phs.vn/browse/PPM-249 | 07/05/2026 | 22/05/2026 |  |  | 12/05/2026 09:09 | 10090329 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2238356] [MSD] [No.27-2025]ADVANCE MARGIN FOR DERIVATIVES | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | MSD | UAT Testing | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-11 | 26/12/2025 |  |  |  | 12/05/2026 08:52 | 10090263 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2084592] [RMD] [No.10-2025] Calculate interest for accounts using special interest rate products | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | RMD | Waiting FTL | App-MW | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-6 | 04/10/2025 |  |  |  | 12/05/2026 08:33 | 10090209 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2222464] [RMD] [No.09-2025] Add sign-in method | huunguyen2525 | huunguyen2525 | huunguyen2525 | [5 empty] | 13/05/2026 10:27 |  | Hoàn thành |  |  | Mobile Team | RMD | Go-live | App-MW | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-137 | 12/12/2025 |  |  |  | 12/05/2026 09:00 | 10090302 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2443571] [SS] [No.09-2026] Restrict using PHS email address for securities transactions | huunguyen2525 | huunguyen2525 | huunguyen2525 | [5 empty] | 05/06/2026 11:06 |  | Hoàn thành |  |  | Mobile Team | SS | UAT Testing | Elite App |  |  |  | 06/05/2026 |  |  |  | 12/05/2026 09:14 | 10090343 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2149046] [SS] [No.28-2025] Adjustment of the account opening flow on the PHS ELITE TRADING application | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | SS | UAT Testing | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-5 | 12/11/2025 |  |  |  | 12/05/2026 08:31 | 10090204 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2133352] [RMD] [No.12-2025] Margin product calculation tool | huunguyen2525 | huunguyen2525 | huunguyen2525 | [5 empty] | 15/05/2026 10:32 |  | Hoàn thành |  |  | Mobile Team | RMD | Go-live | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-9 | 22/10/2025 |  |  |  | 12/05/2026 08:43 | 10090240 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2246969] [DTD] [No.39-2025] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | huunguyen2525 | huunguyen2525 | huunguyen2525 | [5 empty] | 15/05/2026 10:32 |  | Hoàn thành |  |  | Mobile Team | DTD | Go-live | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-10 | 30/12/2025 |  |  |  | 12/05/2026 08:45 | 10090247 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2106995] [DTD] [No.25-2025] Add put-through order trading feature on PHS ELITE XPRO | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | MW Team | DTD | UAT Testing | Xpro | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-94 | 08/10/2025 |  |  |  | 12/05/2026 08:50 | 10090258 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2275303] [DTD] [No.1-2026] Enhance securities depository features via the PHS Elite Trading application | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | SS | FTL Coding | Elite App |  |  | https://dev-ftl-jira.phs.vn/browse/PPM-12 | 27/01/2026 |  |  |  | 12/05/2026 08:57 | 10090293 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2216483] [MSD] [No.33-2025] Loyalty Customer System | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Team B | MSD | Waiting FTL | Elite App, Customer Portal | SS |  | https://dev-ftl-jira.phs.vn/projects/PPM/issues/PPM-230 | 31/12/2025 |  |  |  | 12/05/2026 08:55 | 10090287 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2437753] [SS] [No.07-2026] AF & LN Duplication & Bulk Import Function | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  |  |  | FSS Eval CR | [8 empty] | 12/05/2026 09:08 | 10090323 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
[CR] [2283752] [DTD] [No.03-2026] Send Notification via Elite App and mail all right issue | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | DTD | UAT Testing | Elite App | SS |  | https://dev-ftl-jira.phs.vn/browse/PPM-133 | 27/01/2026 |  |  |  | 12/05/2026 08:56 | 10090289 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
MW Team - Backlog:
[CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling for Customers | huunguyen2525 | huunguyen2525 | huunguyen2525 | [7 empty] | Đang làm |  |  | Mobile Team | FN | Discuss Req | Elite App | FN |  | https://dev-ftl-jira.phs.vn/browse/PPM-191 | 30/01/2026 |  |  |  | 12/05/2026 08:53 | 10090283 | 0 | Task | NGUYỄN MINH HỮU | NGUYỄN MINH HỮU
Team Mobile - Q1:
[CR] [2133352] [RMD] Margin product calculation tool | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 02/03/2026 00:00 | 30/03/2026 23:59 | 30/03/2026 15:00 |  | Hoàn thành |  |  | Mobile Team | RMD | Go-live | Elite App | IT, SS | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-560 | 22/10/2025 |  | FTL, MW, Mobile |  | 03/03/2026 16:39 | 9739420 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2247969] [SS] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 11/03/2026 00:00 | 30/03/2026 23:59 | 30/03/2026 15:00 |  | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-610 | 30/12/2025 | 27/02/2026 | FTL, MW, Mobile | Coding UI | 03/03/2026 16:39 | 9739418 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2186435] [MSD] PROMOTION REGISTRATION FUNCTION UPGRADE | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 02/03/2026 00:00 | 30/03/2026 23:59 | 30/03/2026 14:59 |  | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-660 | 25/11/2025 | 03/02/2026 | FTL, MW, Mobile, Web B |  | 03/03/2026 16:39 | 9739416 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2285823] [IC] THE LOGIN SCREEN GREETING MESSAGE | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 03/03/2026 00:00 | 16/03/2026 23:59 | 16/03/2026 11:11 |  | Hoàn thành |  |  | Mobile Team | IC | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-635 | 27/01/2026 | 02/03/2026 | Mobile |  | 03/03/2026 16:39 | 9739417 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2224919] [SS] Feature to save multiple login accounts on a single device in the PHS Elite Trading app | phongvo2440 | phongvo2440 | phongvo2440 |  |  |  | 26/02/2026 00:00 | 16/03/2026 23:59 | 16/03/2026 11:10 |  | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-535 | 19/12/2025 |  | Mobile |  | 03/03/2026 16:39 | 9739421 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2302697] [LG] Add content regarding personal data protection | phongvo2440 |  | phongvo2440 | [5 empty] | 06/03/2026 08:59 |  | Hoàn thành |  |  | Mobile Team | LG | Rejected | Elite App | IT, SS | 2026Q2 | https://dev-ftl-jira.phs.vn/browse/MEA-735 | 29/01/2026 |  |  | LG rejected this CR | 03/03/2026 16:39 | 9739413 | 0 | Task |  | VÕ THANH PHONG
[CR] [2185585] [IT] Add the Reward Redemption feature to the PHS Elite Trading application | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | IT | Go-live | Elite App | SS, CCC, MKT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-510 | 21/11/2025 | 11/02/2026 | FTL, MW, Mobile, Web B |  | 03/03/2026 16:40 | 9739430 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2154685] [INB] Mutual Fund Distribution (Phase 2) | phongvo2440 |  | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | INB | Go-live | Elite App | IT, SS, FN | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-485 | 11/11/2025 | 10/12/2025 | FTL, MW, Mobile, Web B |  | 03/03/2026 16:40 | 9739431 | 0 | Task |  | VÕ THANH PHONG
[MKT] Update Logo PHS 20 years anniversary | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | MKT | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-460 | 03/02/2026 |  | Mobile |  | 03/03/2026 16:40 | 9739432 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2077975] [MKT] Collaboration with Woori Bank Proposal | phongvo2440 |  | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | MKT | Go-live | Elite App | IT, SS, HR, BMD | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-435 | 19/11/2025 |  | FTL, MW, Mobile |  | 03/03/2026 16:40 | 9739433 | 0 | Task |  | VÕ THANH PHONG
[CR] [2196774] [INB] Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | INB | Go-live | Elite App | IT, SS, FN | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-410 | 12/10/2025 |  | FTL, FSS, MW, Mobile, Web A |  | 03/03/2026 16:40 | 9739434 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2242463] [MSD] PROMOTION: HORSE YEAR FORTUNE 2026 | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | SS | Go-live | Elite App | IT | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-385 |  |  | Mobile, Web A |  | 03/03/2026 16:40 | 9739435 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
[CR] [2185583] [IT] Enhancement of the Smart OTP Function on the PHS Elite Trading Application | phongvo2440 | phongvo2440 | phongvo2440 | [5 empty] | 03/03/2026 16:41 |  | Hoàn thành |  |  | Mobile Team | IT | Go-live | Elite App | SS | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/MEA-360 | 24/11/2025 |  | Mobile |  | 03/03/2026 16:40 | 9739436 | 0 | Task | VÕ THANH PHONG | VÕ THANH PHONG
Dev Team B - Q1:
[CR] [2213580] [CCC] Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | minhvo2565 | minhvo2565 | minhvo2565 | [5 empty] | 17/03/2026 10:52 |  | Hoàn thành |  |  | Team B | CCC | Go-live | Customer Portal | CCC | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/PP-3 | 19/12/2025 | 20/01/2026 | Web B |  | 03/03/2026 15:47 | 9739106 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2186435] [MSD] Enhance Promotion features on Admin Customer Portal | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  | 02/03/2026 00:00 | 09/03/2026 23:59 | 10/03/2026 08:47 |  | Hoàn thành muộn |  |  | Team B | MSD | Go-live | Customer Portal | IT, MSD | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/PP-12 | 25/11/2025 | 22/01/2026 | Web B |  | 03/03/2026 15:47 | 9739108 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [2065876] [MSD] Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | minhvo2565 | minhvo2565 | minhvo2565 | [5 empty] | 04/03/2026 06:56 |  | Hoàn thành |  |  | Team B | MSD | Go-live | Customer Portal | IT, MSD | 2026Q1 | https://dev-ftl-jira.phs.vn/browse/PP-1 | 11/09/2025 | 24/11/2025 | Web B |  | 03/03/2026 15:46 | 9739105 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH
[CR] [1722552] [BMD] Provide API data source for Transaction fluctuation function in Broker portal | minhvo2565 | minhvo2565 | minhvo2565 |  |  |  |  | 13/02/2026 23:59 | 04/03/2026 16:29 |  | Hoàn thành muộn |  |  | Team B | BMD | Go-live | Broker Portal | IT | 2026Q1 |  | 26/02/2025 |  | Web B |  | 04/03/2026 16:25 | 9744376 | 0 | Task | VÕ BẢO MINH | VÕ BẢO MINH