## Task Tracker
IT Department — Cross-Team Task Tracker 2026
Request ID | Task ID | Task Name | Team | Category | Dept Tag | Priority | Status | Phase | Assignee | Team Lead | Created Date | Deadline | Completed Date | Dependencies | Notes
2400155 | 10186512 | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | Dev Team B | CR | MKT | Medium | Doing | Q2 |  | minhvo@phs.vn | 01/06/2026 08:13 | 09/06/2026 23:59 |  | 2400155
2084592 | 10055830 | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | Dev Team B | CR | RMD | High | Done | Q2 |  | minhvo@phs.vn | 05/05/2026 17:37 | 15/05/2026 23:59 | 16/05/2026 08:01 | 2084592
2275303 | 9953933 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Dev Team B | CR | SS | High | Done | Q2 |  | minhvo@phs.vn | 13/04/2026 22:08 | 04/05/2026 23:59 | 05/05/2026 17:42 | 2275303
2329940 | 9739428 | [CR] [2329940] [RS] AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | Team Mobile | CR | RS | High | Overdue | Q2 |  | phongvo@phs.vn | 03/03/2026 16:40 | 22/05/2026 23:59
2275303 | 9739429 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Team Mobile | CR | SS | High | Overdue | Q2 |  | phongvo@phs.vn | 03/03/2026 16:40 | 26/05/2026 23:59 |  | 2275303
2084592 | 9739419 | [CR] [2084592] [RMD] Declare Limit & Type For Account Using Special Product on FLEX system | Team Mobile | CR | RMD | High | Overdue | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 | 31/05/2026 23:59 |  | 2084592
2149046 | 9739414 | [CR] [2149046] [IT] EKYC | Team Mobile | CR | IT | High | Overdue | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 | 22/05/2026 23:59 |  | 2149046
2283752 | 9739427 | [CR] [2283752] [SS] Send Notification via Elite App and mail all right issue | Team Mobile | CR | SS | Low | Doing | Q2 |  | phongvo@phs.vn | 03/03/2026 16:40 |  |  | 2283752
2238356 | 9739415 | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | Team Mobile | CR | MSD | High | Overdue | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 | 29/05/2026 23:59 |  | 2238356
2335404 | 9953694 | [CR] [2335404] Upgrade the automatic limit adjustment feature | Team Mobile | CR |  | Medium | Doing | Q2 |  | phongvo@phs.vn | 13/04/2026 17:22 | 26/06/2026 23:59 |  | 2335404
2400155 | 9953677 | [CR] [2400155] Marketing - Develop Mission Tracking Page for Promotion Q1.2026 | Team Mobile | CR |  | Medium | Doing | Q2 |  | phongvo@phs.vn | 13/04/2026 17:14 | 09/06/2026 23:59 |  | 2400155
2335404 | 10198123 | [CR] [2335404] [RMD] Upgrade the automatic limit adjustment feature on Customer Portal Admin | Dev Team B | CR | RMD | Medium | Doing | Q2 |  | minhvo@phs.vn | 03/06/2026 13:38 | 12/06/2026 23:59 |  | 2335404
2400155 | 9956961 | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | Dev Team B | CR | MKT | Medium | Doing | Q2 |  | minhvo@phs.vn | 14/04/2026 09:43 |  |  | 2400155
2403987 | 10059258 | [CR] [2403987] [SS] Loyalty System - Phase 1 | Dev Team B | CR | SS | Medium | Doing | Q2 |  | minhvo@phs.vn | 06/05/2026 13:54 | 23/11/2026 23:59
2129248 | 9956514 | [CR] [2129248] [RMD] Add Special room information for Locations | Dev Team B | CR | RMD | Low | Doing | Q2 |  | minhvo@phs.vn | 14/04/2026 09:18
2084592 | 9956972 | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | Dev Team B | CR | RMD | High | Doing | Q2 |  | minhvo@phs.vn | 14/04/2026 09:44 |  |  | 2084592
2275303 | 9956507 | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Dev Team B | CR | SS | High | Done | Q2 |  | minhvo@phs.vn | 14/04/2026 09:17 | 04/05/2026 23:59 | 05/05/2026 17:43 | 2275303
2423945 | 10055837 | [CR] [2423945] [SS] Enhance the promotional declaration feature on the Admin Portal | Dev Team B | CR | SS | Low | Done | Q2 |  | minhvo@phs.vn | 05/05/2026 17:48 |  | 01/06/2026 08:11
2154685 | 9956498 | [CR] [2154685] [BMD] Upgrade fund certificate trading feature on Mobile app | Dev Team B | CR | BMD | Medium | Done | Q2 |  | minhvo@phs.vn | 14/04/2026 09:15 | 28/04/2026 23:59 | 05/05/2026 14:36 | 2154685
2385402 | 9956496 | [CR] [2385402] [MKT] Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | Dev Team B | CR | MKT | Low | Done | Q2 |  | minhvo@phs.vn | 14/04/2026 09:15 |  | 25/04/2026 09:17
2197982 | 9956499 | [CR] [2197982] [RS] Research Landing Page: All Features & Phase 1 Execution | Dev Team B | CR | RS | Low | Done | Q2 |  | minhvo@phs.vn | 14/04/2026 09:16 |  | 20/04/2026 08:28
1954732 | 10058431 | [CR] [1954732] [HR] HR report automation | Dev Team B | CR | HR | Low | Todo | Backlog |  | minhvo@phs.vn | 06/05/2026 08:34
2426812 | 10058420 | [CR] [2426812] [MKT] Merge CCC & RS chatbot into one Master Client Chatbot | Dev Team B | CR | MKT | Low | Todo | Backlog |  | minhvo@phs.vn | 06/05/2026 08:31
2415056 | 10058445 | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | Dev Team B | CR | MKT | Low | Todo | Backlog |  | minhvo@phs.vn | 06/05/2026 08:40
2330515 | 10058441 | [CR] [2330515] [RMD] IPO Share Subscription Feature | Dev Team B | CR | RMD | Low | Todo | Backlog |  | minhvo@phs.vn | 06/05/2026 08:36 |  |  | 2330515
2425861 | 10058456 | [CR] [2425861] [RS] Research Portal: Phase 2 | Dev Team B | CR | RS | Low | Todo | Backlog |  | minhvo@phs.vn | 06/05/2026 08:43
1923581 | 9956873 | [CR] [1923581] [RMD] Tool to control the number of positions that need to be closed out | Dev Team B | CR | RMD | Low | Todo | Backlog |  | minhvo@phs.vn | 14/04/2026 09:25
2306127 | 9931785 | [CR] [2306127] INB_ Proposal to implement the mobile app notifications for Elite Seeds | Team Mobile | CR |  | Low | Done | Q2 |  | phongvo@phs.vn | 09/04/2026 17:00 |  | 27/05/2026 13:29
2372910 | 10007137 | [CR][2372910] [RESEARCH] Permission to get API data from OpenAcc web | Team Mobile | CR |  | Low | Done | Q2 |  | phongvo@phs.vn | 24/04/2026 09:27 |  | 04/05/2026 08:26
2216483 | 9739424 | [CR] [2216483] [MSD] LOYALTY SYSTEM ON MOBILE APP | Team Mobile | CR | MSD | Low | Done | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 |  | 04/05/2026 08:15 | 2216483
2400512 | 9931751 | [SDK] [2400512] Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google | Team Mobile | SDK |  | Low | Done | Q2 |  | phongvo@phs.vn | 09/04/2026 16:57 |  | 20/04/2026 08:12
2222464 | 9739423 | [CR] [2222464] [RMD] Add sign-in method | Team Mobile | CR | RMD | Low | Done | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 |  | 20/04/2026 08:11 | 2222464
2212813 | 9739422 | [CR] [2212813] [SS] Derivatives Order Placement UI Enhancement | Team Mobile | CR | SS | Low | Done | Q2 |  | phongvo@phs.vn | 03/03/2026 16:39 |  | 13/04/2026 17:02
2397922 | 9953690 | [CR] [2397922] Enhance filter for Elite Fund | Team Mobile | CR |  | Low | Todo | Backlog |  | phongvo@phs.vn | 13/04/2026 17:21
2376660 | 9953687 | [CR] [2376660] Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | Team Mobile | CR |  | Low | Todo | Backlog |  | phongvo@phs.vn | 13/04/2026 17:20
2307583 | 9953685 | [CR] [2307583] PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | Team Mobile | CR |  | Low | Todo | Backlog |  | phongvo@phs.vn | 13/04/2026 17:18
2330515 | 9953664 | [CR] [2330515] IPO Share Subscription Feature | Team Mobile | CR |  | Low | Todo | Backlog |  | phongvo@phs.vn | 13/04/2026 17:11 |  |  | 2330515
2310394 | 9953652 | [CR] [2310394] Tax analysis and estimation tools for investors (Phase 1) | Team Mobile | CR |  | Low | Todo | Backlog |  | phongvo@phs.vn | 13/04/2026 17:05
2289280 | 9739426 | [CR] [2289280] [FN] Future-Dated Withdrawal Scheduling for Customers | Team Mobile | CR | FN | Low | Todo | Backlog |  | phongvo@phs.vn | 03/03/2026 16:40 |  |  | 2289280
2317336 | 9739425 | [CR] [2317336] [AC] Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | Team Mobile | CR | AC | Low | Todo | Backlog |  | phongvo@phs.vn | 03/03/2026 16:40
2174942 | 9739412 | [CR] [2174942] [MSD] Automation Test Proposal | Team Mobile | CR | MSD | Low | Todo | Backlog |  | phongvo@phs.vn | 03/03/2026 16:39
| 10090312 | [CR] [2310394 - 2391899] [KT] [No.01-2026] Tax analysis and estimation tools for investors. | MW Team | CR |  | Medium | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 09:03
2446191 | 10090329 | [CR] [2446191] [MSD] [No.08-2026] VCF0051 – Adjust Report Extraction Conditions | MW Team | CR | MSD | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 09:09
2238356 | 10090263 | [CR] [2238356] [MSD] [No.27-2025]ADVANCE MARGIN FOR DERIVATIVES | MW Team | CR | MSD | High | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:52 |  |  | 2238356
2084592 | 10090209 | [CR] [2084592] [RMD] [No.10-2025] Calculate interest for accounts using special interest rate products | MW Team | CR | RMD | High | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:33 |  |  | 2084592
2222464 | 10090302 | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | MW Team | CR | RMD | Low | Done | Q2 |  | huunguyen@phs.vn | 12/05/2026 09:00 |  | 13/05/2026 10:27 | 2222464
2443571 | 10090343 | [CR] [2443571] [SS] [No.09-2026] Restrict using PHS email address for securities transactions | MW Team | CR | SS | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 09:14
2149046 | 10090204 | [CR] [2149046] [SS] [No.28-2025] Adjustment of the account opening flow on the PHS ELITE TRADING application | MW Team | CR | SS | High | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:31 |  |  | 2149046
2133352 | 10090240 | [CR] [2133352] [RMD] [No.12-2025] Margin product calculation tool | MW Team | CR | RMD | Medium | Done | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:43 |  | 15/05/2026 10:32 | 2133352
2246969 | 10090247 | [CR] [2246969] [DTD] [No.39-2025] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | MW Team | CR | DTD | Low | Done | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:45 |  | 15/05/2026 10:32
2106995 | 10090258 | [CR] [2106995] [DTD] [No.25-2025] Add put-through order trading feature on PHS ELITE XPRO | MW Team | CR | DTD | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:50
2275303 | 10090293 | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository features via the PHS Elite Trading application | MW Team | CR | DTD | High | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:57 |  |  | 2275303
2216483 | 10090287 | [CR] [2216483] [MSD] [No.33-2025] Loyalty Customer System | MW Team | CR | MSD | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:55 |  |  | 2216483
2437753 | 10090323 | [CR] [2437753] [SS] [No.07-2026] AF & LN Duplication & Bulk Import Function | MW Team | CR | SS | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 09:08
2283752 | 10090289 | [CR] [2283752] [DTD] [No.03-2026] Send Notification via Elite App and mail all right issue | MW Team | CR | DTD | Low | Doing | Q2 |  | huunguyen@phs.vn | 12/05/2026 08:56 |  |  | 2283752
2289280 | 10090283 | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling for Customers | MW Team | CR | FN | Low | Todo | Backlog |  | huunguyen@phs.vn | 12/05/2026 08:53 |  |  | 2289280
2133352 | 9739420 | [CR] [2133352] [RMD] Margin product calculation tool | Team Mobile | CR | RMD | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 | 30/03/2026 23:59 | 30/03/2026 15:00 | 2133352
2247969 | 9739418 | [CR] [2247969] [SS] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | Team Mobile | CR | SS | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 | 30/03/2026 23:59 | 30/03/2026 15:00
2186435 | 9739416 | [CR] [2186435] [MSD] PROMOTION REGISTRATION FUNCTION UPGRADE | Team Mobile | CR | MSD | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 | 30/03/2026 23:59 | 30/03/2026 14:59 | 2186435
2285823 | 9739417 | [CR] [2285823] [IC] THE LOGIN SCREEN GREETING MESSAGE | Team Mobile | CR | IC | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 | 16/03/2026 23:59 | 16/03/2026 11:11
2224919 | 9739421 | [CR] [2224919] [SS] Feature to save multiple login accounts on a single device in the PHS Elite Trading app | Team Mobile | CR | SS | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 | 16/03/2026 23:59 | 16/03/2026 11:10
2302697 | 9739413 | [CR] [2302697] [LG] Add content regarding personal data protection | Team Mobile | CR | LG | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:39 |  | 06/03/2026 08:59
2185585 | 9739430 | [CR] [2185585] [IT] Add the Reward Redemption feature to the PHS Elite Trading application | Team Mobile | CR | IT | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2154685 | 9739431 | [CR] [2154685] [INB] Mutual Fund Distribution (Phase 2) | Team Mobile | CR | INB | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41 | 2154685
| 9739432 | [MKT] Update Logo PHS 20 years anniversary | Team Mobile | Internal |  | Medium | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2077975 | 9739433 | [CR] [2077975] [MKT] Collaboration with Woori Bank Proposal | Team Mobile | CR | MKT | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2196774 | 9739434 | [CR] [2196774] [INB] Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | Team Mobile | CR | INB | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2242463 | 9739435 | [CR] [2242463] [MSD] PROMOTION: HORSE YEAR FORTUNE 2026 | Team Mobile | CR | MSD | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2185583 | 9739436 | [CR] [2185583] [IT] Enhancement of the Smart OTP Function on the PHS Elite Trading Application | Team Mobile | CR | IT | Low | Done | Q1 |  | phongvo@phs.vn | 03/03/2026 16:40 |  | 03/03/2026 16:41
2213580 | 9739106 | [CR] [2213580] [CCC] Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | Dev Team B | CR | CCC | Low | Done | Q1 |  | minhvo@phs.vn | 03/03/2026 15:47 |  | 17/03/2026 10:52
2186435 | 9739108 | [CR] [2186435] [MSD] Enhance Promotion features on Admin Customer Portal | Dev Team B | CR | MSD | Medium | Done | Q1 |  | minhvo@phs.vn | 03/03/2026 15:47 | 09/03/2026 23:59 | 10/03/2026 08:47 | 2186435
2065876 | 9739105 | [CR] [2065876] [MSD] Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | Dev Team B | CR | MSD | Low | Done | Q1 |  | minhvo@phs.vn | 03/03/2026 15:46 |  | 04/03/2026 06:56
1722552 | 9744376 | [CR] [1722552] [BMD] Provide API data source for Transaction fluctuation function in Broker portal | Dev Team B | CR | BMD | Medium | Done | Q1 |  | minhvo@phs.vn | 04/03/2026 16:25 | 13/02/2026 23:59 | 04/03/2026 16:29

## Team Config
Team Name | Team Lead | Lead Email | Members Count
Team Mobile | Phong Vo | phongvo@phs.vn
Dev Team B | Minh Vo | minhvo@phs.vn
MW Team | Huu Nguyen | huunguyen@phs.vn

## Naming Convention
Task Naming Convention Guide
Pattern | Example | Description | Field Mapping
[CR] [request-id] [dept] Title | [CR] [2329940] [RS] AI Chatbot Integration | Standard CR task — request-id is the ID from the base request platform | Request ID → column A
[CR] [request-id] [dept] [No.XX-YYYY] Title | [CR] [2084592] [RMD] [No.10-2025] Calculate interest | MW Team format with internal sequence number and year | No.XX-YYYY tracks internal ordering
[SDK] [request-id] Title | [SDK] [2400512] Upgrade iOS and Android SDKs | SDK upgrade tasks | Category = SDK
[dept] Title (no CR) | [MKT] Update Logo PHS 20 years anniversary | Internal task without CR number | Category = Internal
Mandatory Fields & Rules
1. Every task MUST have: Request ID, Task Name, Team, Status, Assignee, Team Lead, Created Date, Deadline.
2. Backlog tasks: Status = "Todo", Phase = "Backlog". Must be groomed with deadline before moving to "Doing".
3. Request ID is the unique identifier from the base request platform — use it to detect duplicates across teams.
4. If the same CR spans multiple teams, create ONE row per team with the SAME Request ID. Use Dependencies column to link them.
5. Status flow: Todo → Doing → Done ¦ Todo → Doing → Overdue → Done ¦ Any → Blocked (explain in Notes).
6. Multi-team CRs: When a CR spans multiple teams, append the team scope to the task name: [CR] [request-id] [dept] Title — Scope (e.g., "— Mobile UI", "— Middleware API", "— Web Admin"). Use the SAME Request ID across all rows.
7. CR Overview sheet: For every multi-team CR, maintain ONE row in the CR Overview sheet summarizing all teams’ statuses. Update the Overall Status whenever any team’s status changes.

## Dashboard Summary
Auto-calculated Dashboard (COUNTIFS from Task Tracker)
Team | Total | Todo | Doing | Done | Overdue | Blocked
Team Mobile
Dev Team B
MW Team
TOTAL
Breakdown by Phase
Team | Q1 | Q2 | Q3 | Q4 | Backlog | Total
Team Mobile
Dev Team B
MW Team

## CR Overview
CR Overview — Cross-Team Change Request Tracking
Each row = one unique CR. Shows which teams are involved, per-team status, and overall CR health. Manually maintained — reference Task Tracker for source data.
Request ID | CR Title | Dept | Priority | Teams Involved | Mobile Status | Dev B Status | MW Status | Overall Status | Blockers / Notes
2084592 | Calculate interest for accounts using special interest rate products | RMD | High | 3 teams | Overdue | Doing | Doing | Overdue | Team Mobile: overdue (deadline 31/05/2026). Dev Team B: no deadline set. MW Team: no deadline set
2275303 | Enhance securities depository features via the PHS Elite Trading application | SS | High | 3 teams | Overdue | Done | Doing | Overdue | Team Mobile: overdue (deadline 26/05/2026). MW Team: no deadline set
2149046 | EKYC | IT | High | 2 teams | Overdue | — | Doing | Overdue | Team Mobile: overdue (deadline 22/05/2026). MW Team: no deadline set
2238356 | ADVANCE MARGIN FOR DERIVATIVES | MSD | High | 2 teams | Overdue | — | Doing | Overdue | Team Mobile: overdue (deadline 29/05/2026). MW Team: no deadline set
2133352 | Margin product calculation tool | RMD | Medium | 2 teams | Done | — | Done | Done
2154685 | Upgrade fund certificate trading feature on Mobile app | BMD | Medium | 2 teams | Done | Done | — | Done
2186435 | PROMOTION REGISTRATION FUNCTION UPGRADE | MSD | Medium | 2 teams | Done | Done | — | Done
2335404 | Upgrade the automatic limit adjustment feature |  | Medium | 2 teams | Doing | Doing | — | In Progress
2400155 | Develop Mission Tracking Page for Promotion | MKT | Medium | 2 teams | Doing | Doing | — | In Progress | Dev Team B: no deadline set
2216483 | LOYALTY SYSTEM ON MOBILE APP | MSD | Low | 2 teams | Done | — | Doing | Partially Done | MW Team: no deadline set
2222464 | Add sign-in method | RMD | Low | 2 teams | Done | — | Done | Done
2283752 | Send Notification via Elite App and mail all right issue | SS | Low | 2 teams | Doing | — | Doing | In Progress | Team Mobile: no deadline set. MW Team: no deadline set
2289280 | Future-Dated Withdrawal Scheduling for Customers | FN | Low | 2 teams | Todo | — | Todo | Not Started
2330515 | IPO Share Subscription Feature | RMD | Low | 2 teams | Todo | Todo | — | Not Started
2329940 | AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | RS | High | 1 team | Overdue | — | — | Overdue | Team Mobile: overdue (deadline 22/05/2026)
1722552 | Provide API data source for Transaction fluctuation function in Broker portal | BMD | Medium | 1 team | — | Done | — | Done
2224919 | Feature to save multiple login accounts on a single device in the PHS Elite Trading app | SS | Medium | 1 team | Done | — | — | Done
2247969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | SS | Medium | 1 team | Done | — | — | Done
2285823 | THE LOGIN SCREEN GREETING MESSAGE | IC | Medium | 1 team | Done | — | — | Done
2403987 | Loyalty System - Phase 1 | SS | Medium | 1 team | — | Doing | — | In Progress
1923581 | Tool to control the number of positions that need to be closed out | RMD | Low | 1 team | — | Todo | — | Not Started
1954732 | HR report automation | HR | Low | 1 team | — | Todo | — | Not Started
2065876 | Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | MSD | Low | 1 team | — | Done | — | Done
2077975 | Collaboration with Woori Bank Proposal | MKT | Low | 1 team | Done | — | — | Done
2106995 | Add put-through order trading feature on PHS ELITE XPRO | DTD | Low | 1 team | — | — | Doing | In Progress | MW Team: no deadline set
2129248 | Add Special room information for Locations | RMD | Low | 1 team | — | Doing | — | In Progress | Dev Team B: no deadline set
2174942 | Automation Test Proposal | MSD | Low | 1 team | Todo | — | — | Not Started
2185583 | Enhancement of the Smart OTP Function on the PHS Elite Trading Application | IT | Low | 1 team | Done | — | — | Done
2185585 | Add the Reward Redemption feature to the PHS Elite Trading application | IT | Low | 1 team | Done | — | — | Done
2196774 | Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | INB | Low | 1 team | Done | — | — | Done
2197982 | Research Landing Page: All Features & Phase 1 Execution | RS | Low | 1 team | — | Done | — | Done
2212813 | Derivatives Order Placement UI Enhancement | SS | Low | 1 team | Done | — | — | Done
2213580 | Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | CCC | Low | 1 team | — | Done | — | Done
2242463 | PROMOTION: HORSE YEAR FORTUNE 2026 | MSD | Low | 1 team | Done | — | — | Done
2246969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | DTD | Low | 1 team | — | — | Done | Done
2302697 | Add content regarding personal data protection | LG | Low | 1 team | Done | — | — | Done
2306127 | INB_ Proposal to implement the mobile app notifications for Elite Seeds |  | Low | 1 team | Done | — | — | Done
2307583 | PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds |  | Low | 1 team | Todo | — | — | Not Started
2310394 | Tax analysis and estimation tools for investors (Phase 1) |  | Low | 1 team | Todo | — | — | Not Started
2317336 | Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | AC | Low | 1 team | Todo | — | — | Not Started
2372910 | [RESEARCH] Permission to get API data from OpenAcc web |  | Low | 1 team | Done | — | — | Done
2376660 | Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project |  | Low | 1 team | Todo | — | — | Not Started
2385402 | Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | MKT | Low | 1 team | — | Done | — | Done
2397922 | Enhance filter for Elite Fund |  | Low | 1 team | Todo | — | — | Not Started
2400512 | Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google |  | Low | 1 team | Done | — | — | Done
2415056 | Implementation of “Partner Offers” on PHS Mobile App | MKT | Low | 1 team | — | Todo | — | Not Started
2423945 | Enhance the promotional declaration feature on the Admin Portal | SS | Low | 1 team | — | Done | — | Done
2425861 | Research Portal: Phase 2 | RS | Low | 1 team | — | Todo | — | Not Started
2426812 | Merge CCC & RS chatbot into one Master Client Chatbot | MKT | Low | 1 team | — | Todo | — | Not Started
2437753 | AF & LN Duplication & Bulk Import Function | SS | Low | 1 team | — | — | Doing | In Progress | MW Team: no deadline set
2443571 | Restrict using PHS email address for securities transactions | SS | Low | 1 team | — | — | Doing | In Progress | MW Team: no deadline set
2446191 | VCF0051 – Adjust Report Extraction Conditions | MSD | Low | 1 team | — | — | Doing | In Progress | MW Team: no deadline set
Summary
Total unique CRs:
Multi-team CRs:
CRs with Overdue status:
CRs fully Done:
CRs Partially Done:
CRs In Progress:
CRs Blocked: