## Task Tracker
IT Department — Cross-Team Task Tracker 2026
Request ID | Task ID | Task Name | Team | Category | Dept Tag | Priority | Status | Phase | Assignee | Team Lead | Created Date | Deadline | Completed Date | Dependencies | Notes
2400155 |  | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | Dev Team B | CR | MKT | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2400155
2084592 |  | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | Dev Team B | CR | RMD | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2084592
2275303 |  | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Dev Team B | CR | SS | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2275303
2275303 |  | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Team Mobile | CR | SS | Medium |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440 | 2275303
2084592 |  | [CR] [2084592] [RMD] Declare Limit & Type For Account Using Special Product on FLEX system | Team Mobile | CR | RMD | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2084592
2149046 |  | [CR] [2149046] [IT] EKYC | Team Mobile | CR | IT | Medium |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440 | 2149046
2283752 |  | [CR] [2283752] [SS] Send Notification via Elite App and mail all right issue | Team Mobile | CR | SS | Medium |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440 | 2283752
2238356 |  | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | Team Mobile | CR | MSD | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2238356
2335404 |  | [CR] [2335404] Upgrade the automatic limit adjustment feature | Team Mobile | CR |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2335404
2400155 |  | [CR] [2400155] Marketing - Develop Mission Tracking Page for Promotion Q1.2026 | Team Mobile | CR |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2400155
2310394 |  | [CR] [2310394] Tax analysis and estimation tools for investors (Phase 1) | Team Mobile | CR |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2335404 |  | [CR] [2335404] [RMD] Upgrade the automatic limit adjustment feature on Customer Portal Admin | Dev Team B | CR | RMD | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2335404
2400155 |  | [CR] [2400155] [MKT] Develop Mission Tracking Page for Promotion | Dev Team B | CR | MKT | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2400155
2403987 |  | [CR] [2403987] [SS] Loyalty System - Phase 1 | Dev Team B | CR | SS | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2129248 |  | [CR] [2129248] [RMD] Add Special room information for Locations | Dev Team B | CR | RMD | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2084592 |  | [CR] [2084592] [RMD] Calculate interest for accounts using special interest rate products | Dev Team B | CR | RMD | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2084592
2275303 |  | [CR] [2275303] [SS] Enhance securities depository features via the PHS Elite Trading application | Dev Team B | CR | SS | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2275303
2423945 |  | [CR] [2423945] [SS] Enhance the promotional declaration feature on the Admin Portal | Dev Team B | CR | SS | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2154685 |  | [CR] [2154685] [BMD] Upgrade fund certificate trading feature on Mobile app | Dev Team B | CR | BMD | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2154685
2385402 |  | [CR] [2385402] [MKT] Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | Dev Team B | CR | MKT | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2197982 |  | [CR] [2197982] [RS] Research Landing Page: All Features & Phase 1 Execution | Dev Team B | CR | RS | Medium |  | Q2 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
1954732 |  | [CR] [1954732] [HR] HR report automation | Dev Team B | CR | HR | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2426812 |  | [CR] [2426812] [MKT] Merge CCC & RS chatbot into one Master Client Chatbot | Dev Team B | CR | MKT | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2415056 |  | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | Dev Team B | CR | MKT | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2415056
2330515 |  | [CR] [2330515] [RMD] IPO Share Subscription Feature | Dev Team B | CR | RMD | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2330515
2425861 |  | [CR] [2425861] [RS] Research Portal: Phase 2 | Dev Team B | CR | RS | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
1923581 |  | [CR] [1923581] [RMD] Tool to control the number of positions that need to be closed out | Dev Team B | CR | RMD | Medium |  | Backlog |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2329940 |  | [CR] [2329940] [RS] AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | Team Mobile | CR | RS | Low |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440
2306127 |  | [CR] [2306127] INB_ Proposal to implement the mobile app notifications for Elite Seeds | Team Mobile | CR |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2372910 |  | [CR][2372910] [RESEARCH] Permission to get API data from OpenAcc web | Team Mobile | CR |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2216483 |  | [CR] [2216483] [MSD] LOYALTY SYSTEM ON MOBILE APP | Team Mobile | CR | MSD | Medium |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440 | 2216483
2400512 |  | [SDK] [2400512] Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google | Team Mobile | SDK |  | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2222464 |  | [CR] [2222464] [RMD] Add sign-in method | Team Mobile | CR | RMD | Medium |  | Q2 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2222464
2212813 |  | [CR] [2212813] [SS] Derivatives Order Placement UI Enhancement | Team Mobile | CR | SS | Low |  | Q2 |  | phongvo@phs.vn |  |  | phongvo2440
2174942 |  | [CR] [2174942] [MSD] Automation Test Proposal | Team Mobile | CR | MSD | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2289280 |  | [CR] [2289280] [FN] Future-Dated Withdrawal Scheduling for Customers | Team Mobile | CR | FN | Medium |  | Backlog |  | phongvo@phs.vn |  |  | phongvo2440 | 2289280
2317336 |  | [CR] [2317336] [AC] Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | Team Mobile | CR | AC | Low |  | Backlog |  | phongvo@phs.vn |  |  | phongvo2440
2307583 |  | [CR] [2307583] PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds | Team Mobile | CR |  | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2330515 |  | [CR] [2330515] IPO Share Subscription Feature | Team Mobile | CR |  | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2330515
2376660 |  | [CR] [2376660] Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project | Team Mobile | CR |  | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2397922 |  | [CR] [2397922] Enhance filter for Elite Fund | Team Mobile | CR |  | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2415056 |  | [CR] [2415056] [MKT] Implementation of “Partner Offers” on PHS Mobile App | Team Mobile | CR | MKT | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2415056
2291957 |  | [CR] [2291957] [IC] Update the account opening function on the PHS Elite app login screen | Team Mobile | CR | IC | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2482578 |  | [CR] [2482578] [AC] Upgrade the QR Code Deposit Function on the PHS App | Team Mobile | CR | AC | Medium |  | Backlog |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
|  | [CR] [2310394 - 2391899] [KT] [No.01-2026] Tax analysis and estimation tools for investors. | MW Team | CR |  | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2446191 |  | [CR] [2446191] [MSD] [No.08-2026] VCF0051 – Adjust Report Extraction Conditions | MW Team | CR | MSD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2238356 |  | [CR] [2238356] [MSD] [No.27-2025]ADVANCE MARGIN FOR DERIVATIVES | MW Team | CR | MSD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2238356
2084592 |  | [CR] [2084592] [RMD] [No.10-2025] Calculate interest for accounts using special interest rate products | MW Team | CR | RMD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2084592
2222464 |  | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | MW Team | CR | RMD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2222464
2443571 |  | [CR] [2443571] [SS] [No.09-2026] Restrict using PHS email address for securities transactions | MW Team | CR | SS | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2149046 |  | [CR] [2149046] [SS] [No.28-2025] Adjustment of the account opening flow on the PHS ELITE TRADING application | MW Team | CR | SS | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2149046
2133352 |  | [CR] [2133352] [RMD] [No.12-2025] Margin product calculation tool | MW Team | CR | RMD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2133352
2246969 |  | [CR] [2246969] [DTD] [No.39-2025] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | MW Team | CR | DTD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2106995 |  | [CR] [2106995] [DTD] [No.25-2025] Add put-through order trading feature on PHS ELITE XPRO | MW Team | CR | DTD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2275303 |  | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository features via the PHS Elite Trading application | MW Team | CR | DTD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2275303
2216483 |  | [CR] [2216483] [MSD] [No.33-2025] Loyalty Customer System | MW Team | CR | MSD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2216483
2437753 |  | [CR] [2437753] [SS] [No.07-2026] AF & LN Duplication & Bulk Import Function | MW Team | CR | SS | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525
2283752 |  | [CR] [2283752] [DTD] [No.03-2026] Send Notification via Elite App and mail all right issue | MW Team | CR | DTD | Medium |  | Q2 |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2283752
2289280 |  | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling for Customers | MW Team | CR | FN | Medium |  | Backlog |  | huunguyen@phs.vn |  | huunguyen2525 | huunguyen2525 | 2289280
2133352 |  | [CR] [2133352] [RMD] Margin product calculation tool | Team Mobile | CR | RMD | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2133352
2247969 |  | [CR] [2247969] [SS] Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | Team Mobile | CR | SS | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2186435 |  | [CR] [2186435] [MSD] PROMOTION REGISTRATION FUNCTION UPGRADE | Team Mobile | CR | MSD | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440 | 2186435
2285823 |  | [CR] [2285823] [IC] THE LOGIN SCREEN GREETING MESSAGE | Team Mobile | CR | IC | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2224919 |  | [CR] [2224919] [SS] Feature to save multiple login accounts on a single device in the PHS Elite Trading app | Team Mobile | CR | SS | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2302697 |  | [CR] [2302697] [LG] Add content regarding personal data protection | Team Mobile | CR | LG | Low |  | Q1 |  | phongvo@phs.vn |  |  | phongvo2440
2185585 |  | [CR] [2185585] [IT] Add the Reward Redemption feature to the PHS Elite Trading application | Team Mobile | CR | IT | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2154685 |  | [CR] [2154685] [INB] Mutual Fund Distribution (Phase 2) | Team Mobile | CR | INB | Medium |  | Q1 |  | phongvo@phs.vn |  |  | phongvo2440 | 2154685
|  | [MKT] Update Logo PHS 20 years anniversary | Team Mobile | Internal |  | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2077975 |  | [CR] [2077975] [MKT] Collaboration with Woori Bank Proposal | Team Mobile | CR | MKT | Low |  | Q1 |  | phongvo@phs.vn |  |  | phongvo2440
2196774 |  | [CR] [2196774] [INB] Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | Team Mobile | CR | INB | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2242463 |  | [CR] [2242463] [MSD] PROMOTION: HORSE YEAR FORTUNE 2026 | Team Mobile | CR | MSD | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2185583 |  | [CR] [2185583] [IT] Enhancement of the Smart OTP Function on the PHS Elite Trading Application | Team Mobile | CR | IT | Medium |  | Q1 |  | phongvo@phs.vn |  | phongvo2440 | phongvo2440
2213580 |  | [CR] [2213580] [CCC] Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | Dev Team B | CR | CCC | Medium |  | Q1 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
2186435 |  | [CR] [2186435] [MSD] Enhance Promotion features on Admin Customer Portal | Dev Team B | CR | MSD | Medium |  | Q1 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565 | 2186435
2065876 |  | [CR] [2065876] [MSD] Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | Dev Team B | CR | MSD | Medium |  | Q1 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565
1722552 |  | [CR] [1722552] [BMD] Provide API data source for Transaction fluctuation function in Broker portal | Dev Team B | CR | BMD | Medium |  | Q1 |  | minhvo@phs.vn |  | minhvo2565 | minhvo2565

## Team Config
Team Name | Team Lead | Lead Email | Members Count
Team Mobile | Phong Vo | phongvo@phs.vn
Dev Team B | Minh Vo | minhvo@phs.vn
MW Team | Huu Nguyen | huunguyen@phs.vn

## Naming Convention
Task Naming Convention Guide
Pattern | Example | Description | Field Mapping
[CR] [request-id] [dept] Title | [CR] [2329940] [RS] AI Chatbot Integration | Standard CR task — request-id is the ID from the base request platform | Request ID → column A
[CR] [request-id] [dept] [No.XX-YYYY] Title | [CR] [2084592] [RMD] [No.10-2025] Calculate interest | MW Team format with internal sequence number and year | No.XX-YYYY tracks internal ordering
[SDK] [request-id] Title | [SDK] [2400512] Upgrade iOS and Android SDKs | SDK upgrade tasks | Category = SDK
[dept] Title (no CR) | [MKT] Update Logo PHS 20 years anniversary | Internal task without CR number | Category = Internal
Mandatory Fields & Rules
1. Every task MUST have: Request ID, Task Name, Team, Status, Assignee, Team Lead, Created Date, Deadline.
2. Backlog tasks: Status = "Todo", Phase = "Backlog". Must be groomed with deadline before moving to "Doing".
3. Request ID is the unique identifier from the base request platform — use it to detect duplicates across teams.
4. If the same CR spans multiple teams, create ONE row per team with the SAME Request ID. Use Dependencies column to link them.
5. Status flow: Todo → Doing → Done ¦ Todo → Doing → Overdue → Done ¦ Any → Blocked (explain in Notes).
6. Multi-team CRs: When a CR spans multiple teams, append the team scope to the task name: [CR] [request-id] [dept] Title — Scope (e.g., "— Mobile UI", "— Middleware API", "— Web Admin"). Use the SAME Request ID across all rows.
7. CR Overview sheet: For every multi-team CR, maintain ONE row in the CR Overview sheet summarizing all teams’ statuses. Update the Overall Status whenever any team’s status changes.

## Dashboard Summary
Auto-calculated Dashboard (COUNTIFS from Task Tracker)
Team | Total | Todo | Doing | Done | Overdue | Blocked
Team Mobile
Dev Team B
MW Team
TOTAL
Breakdown by Phase
Team | Q1 | Q2 | Q3 | Q4 | Backlog | Total
Team Mobile
Dev Team B
MW Team

## CR Overview
CR Overview — Cross-Team Change Request Tracking
Each row = one unique CR. Shows which teams are involved, per-team status, and overall CR health. Manually maintained — reference Task Tracker for source data.
Request ID | CR Title | Dept | Priority | Teams Involved | Mobile Status | Dev B Status | MW Status | Overall Status | Blockers / Notes
2084592 | Calculate interest for accounts using special interest rate products | RMD | Medium | 3 teams |  |  |  | In Progress
2275303 | Enhance securities depository features via the PHS Elite Trading application | SS | Medium | 3 teams |  |  |  | In Progress
2133352 | Margin product calculation tool | RMD | Medium | 2 teams |  | — |  | In Progress
2149046 | EKYC | IT | Medium | 2 teams |  | — |  | In Progress
2154685 | Upgrade fund certificate trading feature on Mobile app | BMD | Medium | 2 teams |  |  | — | In Progress
2186435 | PROMOTION REGISTRATION FUNCTION UPGRADE | MSD | Medium | 2 teams |  |  | — | In Progress
2216483 | LOYALTY SYSTEM ON MOBILE APP | MSD | Medium | 2 teams |  | — |  | In Progress
2222464 | Add sign-in method | RMD | Medium | 2 teams |  | — |  | In Progress
2238356 | ADVANCE MARGIN FOR DERIVATIVES | MSD | Medium | 2 teams |  | — |  | In Progress
2283752 | Send Notification via Elite App and mail all right issue | SS | Medium | 2 teams |  | — |  | In Progress
2289280 | Future-Dated Withdrawal Scheduling for Customers | FN | Medium | 2 teams |  | — |  | In Progress
2330515 | IPO Share Subscription Feature | RMD | Medium | 2 teams |  |  | — | In Progress
2335404 | Upgrade the automatic limit adjustment feature |  | Medium | 2 teams |  |  | — | In Progress
2400155 | Develop Mission Tracking Page for Promotion | MKT | Medium | 2 teams |  |  | — | In Progress
2415056 | Implementation of “Partner Offers” on PHS Mobile App | MKT | Medium | 2 teams |  |  | — | In Progress
1722552 | Provide API data source for Transaction fluctuation function in Broker portal | BMD | Medium | 1 team | — |  | — | In Progress
1923581 | Tool to control the number of positions that need to be closed out | RMD | Medium | 1 team | — |  | — | In Progress
1954732 | HR report automation | HR | Medium | 1 team | — |  | — | In Progress
2065876 | Add a feature to view the registration/deletion history of beneficiary accounts (Same-owner transfer) on the Admin Customer Portal | MSD | Medium | 1 team | — |  | — | In Progress
2106995 | Add put-through order trading feature on PHS ELITE XPRO | DTD | Medium | 1 team | — | — |  | In Progress
2129248 | Add Special room information for Locations | RMD | Medium | 1 team | — |  | — | In Progress
2174942 | Automation Test Proposal | MSD | Medium | 1 team |  | — | — | In Progress
2185583 | Enhancement of the Smart OTP Function on the PHS Elite Trading Application | IT | Medium | 1 team |  | — | — | In Progress
2185585 | Add the Reward Redemption feature to the PHS Elite Trading application | IT | Medium | 1 team |  | — | — | In Progress
2196774 | Proposed modifications of Mobile UI and middleware modules to facilitate Elite Seeds sub-account deployment | INB | Medium | 1 team |  | — | — | In Progress
2197982 | Research Landing Page: All Features & Phase 1 Execution | RS | Medium | 1 team | — |  | — | In Progress
2213580 | Enhancement Successful Reward Redemption Notifications via Email and the PHS Elite Trading App | CCC | Medium | 1 team | — |  | — | In Progress
2224919 | Feature to save multiple login accounts on a single device in the PHS Elite Trading app | SS | Medium | 1 team |  | — | — | In Progress
2242463 | PROMOTION: HORSE YEAR FORTUNE 2026 | MSD | Medium | 1 team |  | — | — | In Progress
2246969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | DTD | Medium | 1 team | — | — |  | In Progress
2247969 | Add PCA trading stock labels and implement stock filtering features on the PHS Elite app | SS | Medium | 1 team |  | — | — | In Progress
2285823 | THE LOGIN SCREEN GREETING MESSAGE | IC | Medium | 1 team |  | — | — | In Progress
2291957 | Update the account opening function on the PHS Elite app login screen | IC | Medium | 1 team |  | — | — | In Progress
2306127 | INB_ Proposal to implement the mobile app notifications for Elite Seeds |  | Medium | 1 team |  | — | — | In Progress
2307583 | PHS BondTerm – Fixed-Tenor Bond Investment Package (via Listed Bonds |  | Medium | 1 team |  | — | — | In Progress
2310394 | Tax analysis and estimation tools for investors (Phase 1) |  | Medium | 1 team |  | — | — | In Progress
2372910 | [RESEARCH] Permission to get API data from OpenAcc web |  | Medium | 1 team |  | — | — | In Progress
2376660 | Assessment of Requirements from RAR Center for the VNeID Integration into the eKYC Account Opening Process Project |  | Medium | 1 team |  | — | — | In Progress
2385402 | Create popup on web phs.vn to promote for landing page PHS 20 Years Anniversary | MKT | Medium | 1 team | — |  | — | In Progress
2397922 | Enhance filter for Elite Fund |  | Medium | 1 team |  | — | — | In Progress
2400512 | Upgrade the iOS and Android SDKs in accordance with the requirements of Apple and Google |  | Medium | 1 team |  | — | — | In Progress
2403987 | Loyalty System - Phase 1 | SS | Medium | 1 team | — |  | — | In Progress
2423945 | Enhance the promotional declaration feature on the Admin Portal | SS | Medium | 1 team | — |  | — | In Progress
2425861 | Research Portal: Phase 2 | RS | Medium | 1 team | — |  | — | In Progress
2426812 | Merge CCC & RS chatbot into one Master Client Chatbot | MKT | Medium | 1 team | — |  | — | In Progress
2437753 | AF & LN Duplication & Bulk Import Function | SS | Medium | 1 team | — | — |  | In Progress
2443571 | Restrict using PHS email address for securities transactions | SS | Medium | 1 team | — | — |  | In Progress
2446191 | VCF0051 – Adjust Report Extraction Conditions | MSD | Medium | 1 team | — | — |  | In Progress
2482578 | Upgrade the QR Code Deposit Function on the PHS App | AC | Medium | 1 team |  | — | — | In Progress
2077975 | Collaboration with Woori Bank Proposal | MKT | Low | 1 team |  | — | — | In Progress
2212813 | Derivatives Order Placement UI Enhancement | SS | Low | 1 team |  | — | — | In Progress
2302697 | Add content regarding personal data protection | LG | Low | 1 team |  | — | — | In Progress
2317336 | Proposal to implement an automated cash dividend reinvestment service (Auto-DRIP) on PHS Elite app | AC | Low | 1 team |  | — | — | In Progress
2329940 | AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | RS | Low | 1 team |  | — | — | In Progress
Summary
Total unique CRs:
Multi-team CRs:
CRs with Overdue status:
CRs fully Done:
CRs Partially Done:
CRs In Progress:
CRs Blocked: