## Task Tracker
IT Department — Cross-Team Task Tracker 2026
Request ID | Task ID | Task Name | Team | Category | Dept Tag | Priority | Status | Phase | Assignee | Team Lead | Created Date | Deadline | Completed Date | Dependencies | Notes
2275303 | 9739429 | [CR] [2275303] [SS] Enhance securities depository — Mobile UI | Team Mobile | CR | SS | High | Overdue | Q2 | mobile_dev_1 | phongvo@phs.vn | 03/03/2026 | 26/05/2026 |  | 2275303 | Waiting for MW API
2275303 | 9956507 | [CR] [2275303] [SS] Enhance securities depository — Web Admin | Dev Team B | CR | SS | High | Done | Q2 | devb_dev_1 | minhvo@phs.vn | 14/04/2026 | 04/05/2026 | 05/05/2026 | 2275303
2275303 | 10090293 | [CR] [2275303] [DTD] [No.1-2026] Enhance securities depository — Middleware API | MW Team | CR | DTD | High | Doing | Q2 | mw_dev_1 | huunguyen@phs.vn | 12/05/2026 |  |  |  | Upstream dependency for Mobile
2084592 | 9739419 | [CR] [2084592] [RMD] Special interest rate on FLEX — Mobile UI | Team Mobile | CR | RMD | Critical | Overdue | Q2 | mobile_dev_2 | phongvo@phs.vn | 03/03/2026 | 31/05/2026 |  | 2084592 | Blocked by 3rd-party FLEX
2084592 | 9956972 | [CR] [2084592] [RMD] Special interest rate — Web Portal | Dev Team B | CR | RMD | Critical | Doing | Q2 | devb_dev_2 | minhvo@phs.vn | 14/04/2026 |  |  | 2084592 | Needs deadline
2084592 | 10090209 | [CR] [2084592] [RMD] [No.10-2025] Special interest rate — Middleware | MW Team | CR | RMD | Critical | Doing | Q2 | mw_dev_2 | huunguyen@phs.vn | 12/05/2026 |  |  |  | Carryover from 2025
2400155 | 9953677 | [CR] [2400155] [MKT] Mission Tracking Page — Mobile App | Team Mobile | CR | MKT | Medium | Doing | Q2 | mobile_dev_3 | phongvo@phs.vn | 13/04/2026 | 20/06/2026 |  | 2400155
2400155 | 9956961 | [CR] [2400155] [MKT] Mission Tracking Page — Web Backend | Dev Team B | CR | MKT | Medium | Doing | Q2 | devb_dev_1 | minhvo@phs.vn | 14/04/2026 |  |  | 2400155 | Needs deadline
2149046 | 9739414 | [CR] [2149046] [IT] EKYC | Team Mobile | CR | IT | Critical | Overdue | Q2 | mobile_dev_1 | phongvo@phs.vn | 03/03/2026 | 22/05/2026 |  |  | EKYC vendor dependency
2329940 | 9739428 | [CR] [2329940] [RS] AI Chatbot Integration | Team Mobile | CR | RS | High | Overdue | Q2 | TBD | phongvo@phs.vn | 03/03/2026 | 22/05/2026 |  |  | Depends on RS team API
2238356 | 9739415 | [CR] [2238356] [MSD] ADVANCE MARGIN FOR DERIVATIVES | Team Mobile | CR | MSD | High | Overdue | Q2 | TBD | phongvo@phs.vn | 03/03/2026 | 29/05/2026
2222464 | 10090302 | [CR] [2222464] [RMD] [No.09-2025] Add sign-in method | MW Team | CR | RMD | Medium | Done | Q2 | mw_dev_1 | huunguyen@phs.vn | 12/05/2026 |  | 13/05/2026
2397922 | 9953690 | [CR] [2397922] Enhance filter for Elite Fund | Team Mobile | CR |  | Low | Todo | Backlog | TBD | phongvo@phs.vn | 13/04/2026 |  |  |  | Needs priority & deadline
1954732 | 10058431 | [CR] [1954732] [HR] HR report automation | Dev Team B | CR | HR | Low | Todo | Backlog | TBD | minhvo@phs.vn | 06/05/2026
2289280 | 10090283 | [CR] [2289280] [FN] [No.01-2026] Future-Dated Withdrawal Scheduling | MW Team | CR | FN | Medium | Todo | Backlog | TBD | huunguyen@phs.vn | 12/05/2026

## Team Config
Team Name | Team Lead | Lead Email | Members Count
Team Mobile | Phong Vo | phongvo@phs.vn
Dev Team B | Minh Vo | minhvo@phs.vn
MW Team | Huu Nguyen | huunguyen@phs.vn

## Naming Convention
Task Naming Convention Guide
Pattern | Example | Description | Field Mapping
[CR] [request-id] [dept] Title | [CR] [2329940] [RS] AI Chatbot Integration | Standard CR task — request-id is the ID from the base request platform | Request ID → column A
[CR] [request-id] [dept] [No.XX-YYYY] Title | [CR] [2084592] [RMD] [No.10-2025] Calculate interest | MW Team format with internal sequence number and year | No.XX-YYYY tracks internal ordering
[SDK] [request-id] Title | [SDK] [2400512] Upgrade iOS and Android SDKs | SDK upgrade tasks | Category = SDK
[dept] Title (no CR) | [MKT] Update Logo PHS 20 years anniversary | Internal task without CR number | Category = Internal
Mandatory Fields & Rules
1. Every task MUST have: Request ID, Task Name, Team, Status, Assignee, Team Lead, Created Date, Deadline.
2. Backlog tasks: Status = "Todo", Phase = "Backlog". Must be groomed with deadline before moving to "Doing".
3. Request ID is the unique identifier from the base request platform — use it to detect duplicates across teams.
4. If the same CR spans multiple teams, create ONE row per team with the SAME Request ID. Use Dependencies column to link them.
5. Status flow: Todo → Doing → Done ¦ Todo → Doing → Overdue → Done ¦ Any → Blocked (explain in Notes).
6. Multi-team CRs: When a CR spans multiple teams, append the team scope to the task name: [CR] [request-id] [dept] Title — Scope (e.g., "— Mobile UI", "— Middleware API", "— Web Admin"). Use the SAME Request ID across all rows.
7. CR Overview sheet: For every multi-team CR, maintain ONE row in the CR Overview sheet summarizing all teams’ statuses. Update the Overall Status whenever any team’s status changes.

## Dashboard Summary
Auto-calculated Dashboard (COUNTIFS from Task Tracker)
Team | Total | Todo | Doing | Done | Overdue | Blocked
Team Mobile
Dev Team B
MW Team
TOTAL
Breakdown by Phase
Team | Q1 | Q2 | Q3 | Q4 | Backlog | Total
Team Mobile
Dev Team B
MW Team

## CR Overview
CR Overview — Cross-Team Change Request Tracking
Each row = one unique CR. Shows which teams are involved, per-team status, and overall CR health. Manually maintained — reference Task Tracker for source data.
Request ID | CR Title | Dept | Priority | Teams Involved | Mobile Status | Dev B Status | MW Status | Overall Status | Blockers / Notes
2275303 | Enhance securities depository features via PHS Elite Trading | SS | High | 3 teams | Overdue | Done | Doing | In Progress | Mobile blocked waiting for MW API. Dev B completed web admin portion.
2084592 | Calculate interest for accounts using special interest rate products | RMD | Critical | 3 teams | Overdue | Doing | Doing | Overdue | Mobile overdue (FLEX 3rd-party dependency). MW carryover from 2025. Dev B needs deadline.
2400155 | Develop Mission Tracking Page for Promotion | MKT | Medium | 2 teams | Doing | Doing | — | In Progress | Dev B row missing deadline. Mobile targeting 20/06.
2283752 | Send Notification via Elite App and mail all right issue | SS | Medium | 2 teams | Doing | — | Doing | In Progress | Mobile + MW. No deadline set on either side.
2335404 | Upgrade the automatic limit adjustment feature | RMD | Medium | 2 teams | Doing | Doing | — | In Progress | Mobile (CRs in Coding) + Dev B (Customer Portal Admin).
2216483 | Loyalty Customer System on Mobile App | MSD | Medium | 2 teams | Done | — | Doing | In Progress | Mobile completed. MW still implementing backend.
2149046 | EKYC | IT | Critical | 1 team | Overdue | — | — | Overdue | Blocked by EKYC vendor. Mobile only.
2329940 | AI Chatbot Integration for Elite Mobile App & Xpro Web Trading | RS | High | 1 team | Overdue | — | — | Overdue | Depends on RS team API. Assignee TBD.
2238356 | ADVANCE MARGIN FOR DERIVATIVES | MSD | High | 1 team | Overdue | — | — | Overdue | Mobile only. 3rd-party dependency.
2403987 | Loyalty System - Phase 1 | SS | Medium | 1 team | — | Doing | — | In Progress | Dev B only. Deadline Nov 2026.
2222464 | Add sign-in method | RMD | Medium | 2 teams | Done | — | Done | Done | Mobile Q1 done. MW completed 13/05.
2443571 | Restrict using PHS email for securities transactions | SS | Medium | 1 team | — | — | Doing | In Progress | MW only.
Summary
Total unique CRs:
Multi-team CRs:
CRs with Overdue status:
CRs fully Done:
CRs Blocked: